## Naksha
Naksha Progress Report
District | Name ULB/Town/ City | Circle | Coordinator Name | Active Surveyors | Daily KPI | 1st-Aug | 2nd-Aug | 4th-Aug | 5th-Aug | 6th-Aug | 7th-Aug | 8th-Aug | 9th-Aug | 11th-Aug | 12th-Aug | 13th-Aug | 14th-Aug | 16th-Aug | 18th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | 27th-Aug | 28th-Aug | 29th-Aug | % of 29th-Aug | Total Wards | Running Wards | Total Ward Completed | Pending ward | Completion Date
Bongaigaon | Abhayapuri | Srijangram | Humayun Kabir | 12 | 240 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0 |  | 11 | 0 | 11 | 0
Sonitpur | Dhekiajuli MB | Dhekiajuli | Kunal Hazarika | 9 | 180 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0 |  | 10 | 0 | 10 | 0
Darrang | Mangaldoi MB | Mangaldoi | Kunal Hazarika | 2 | 40 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0 |  | 10 | 0 | 10 | 0
Sivasagar | Sivasagar MB | Sivasagar | Rupam Gogoi | 10 | 200 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0 |  | 14 | 0 | 14 | 0
Barpeta | Barpeta Road | Barnagar | Humayun Kabir | 8 | 160 | 53 | 92 | 6 | 72 | 100 | 116 | 110 | 146 | 112 | 23 | 0 | 114 | 53 | 97 | 118 | 124 | 82 | 82 | 20 | 10 | 103 | 98 | 112 | 93 | 0.58125 | 10 | 4 | 6 | 0 | 20th-September | 31st-July
Bongaigaon | Bongaigaon | Bongaigaon | Humayun Kabir | 14 | 280 | 0 | 62 | 0 | 0 | 76 | 111 | 100 | 75 | 36 | 50 | 0 | 169 | 57 | 52 | 71 | 103 | 66 | 27 | 130 | 112 | 76 | 86 | 148 | 46 | 0.16429 | 25 | 0 | 25 | 0 | 16th-Auguest | 31st-July
Golaghat | Golaghat MB | Golaghat | Dibakar Kalita | 8 | 160 | 0 | 33 | 7 | 63 | 44 | 65 | 31 | 0 | 95 | 118 | 0 | 88 | 0 | 18 | 33 | 63 | 0 | 0 | 0 | 0 | 78 | 113 | 85 | 102 | 0.6375 | 13 | 6 | 6 | 1 | 12th-October
Hojai | Hojai MB | Hojai | Tonmoy Dutta | 11 | 220 | 0 | 49 | 7 | 112 | 123 | 191 | 197 | 162 | 154 | 130 | 0 | 121 | 48 | 53 | 65 | 90 | 26 | 9 | 90 | 112 | 61 | 14 | 8 | 31 | 0.14091 | 19 | 1 | 18 | 0 | 15th-September
Nalbari | Nalbari MB | Nalbari | Humayun Kabir | 27 | 540 | 0 | 35 | 0 | 0 | 133 | 227 | 220 | 0 | 213 | 0 | 0 | 0 | 99 | 0 | 64 | 87 | 0 | 0 | 0 | 0 | 204 | 214 | 194 | 210 | 0.38889 | 17 | 11 | 6 | 0 | 18th-September
Nagaon | Nagaon MB | Nagaon | Tonmoy Dutta | 22 | 440 | 0 | 0 | 0 | 14 | 289 | 324 | 286 | 0 | 242 | 250 | 0 | 337 | 322 | 246 | 135 | 52 | 0 | 0 | 0 | 0 | 249 | 277 | 292 | 298 | 0.67727 | 26 | 12 | 11 | 3 | 12th-October

## Reservey
Reservey Progress report
Sl No | Survey Areas | Co-ordinator | Circle Name | District Name | Surveyor Deployed | Active Surveyor | Total Villages | Village Completed | Pending Villages | Data Verification | Daily KPI | 1st-Aug | 2nd-Aug | 4th-Aug | 5th-Aug | 6th-Aug | 7th-Aug | 8th-Aug | 9th-Aug | 11th-Aug | 12th-Aug | 13th-Aug | 14th-Aug | 16th-Aug | 18th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | 27th-Aug | 28th-Aug | 29th-Aug | % of 29th-Aug | Remarks | Start Date | No of Polygon | Completed Polygon Till Date | End date
1 | NC Forest Reservey | Pradip Saikia | Dhemaji | Dhemaji | 6 | 6 | 8 | 8 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
2 |  | Pradip Saikia | Gogamukh | Dhemaji | 15 | 15 | 18 | 10 | 8 |  | 0 | 164 | 194 | 159 | 241 | 237 | 149 | 77 | 313 | 55 | 338 | 93 | 190 | 253 | 183 | 31 | 16 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
3 |  | Pradip Saikia | Jonai | Dhemaji | 9 | 8 | 22 | 9 | 13 |  | 0 | 87 | 0 | 51 | 0 | 153 | 0 | 98 | 118 | 0 | 87 | 0 | 116 | 8 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
4 |  | Pradip Saikia | Sissiborgaon | Dhemaji | 7 | 0 | 10 | 10 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
5 | Reservey | Ram Kumar Doley | Dibrugarh West | Dibrugarh | 55 | 52 | 169 | 17 | 152 | 5 | 1375 | 0 | 181 | 104 | 320 | 593 | 492 | 463 | 463 | 0 | 328 | 0 | 515 | 397 | 531 | 542 | 214 | 517 | 564 | 583 | 464 | 625 | 561 | 497 | 0 | 0 | Rain
6 |  | Rupam Jyoti Gogoi | Dibrugarh East | Dibrugarh | 37 | 35 | 116 | 0 | 116 | 9 | 925 | 40 | 48 | 34 | 184 | 333 | 279 | 339 | 346 | 0 | 218 | 4 | 318 | 46 | 314 | 325 | 147 | 272 | 290 | 268 | 263 | 300 | 422 | 410 | 54 | 0.058378 | Rain
7 |  | Rupam Jyoti Gogoi | Moran | Dibrugarh | 23 | 18 | 60 | 2 | 57 |  | 575 | 66 | 130 | 135 | 173 | 194 | 267 | 223 | 223 | 174 | 114 | 172 | 166 | 0 | 82 | 141 | 161 | 241 | 207 | 210 | 206 | 219 | 208 | 224 | 210 | 0.36522 | Rain
8 |  | Rupam Jyoti Gogoi | Chabua | Dibrugarh | 27 | 24 | 104 | 2 | 102 | 7 | 675 | 0 | 20 | 26 | 12 | 260 | 335 | 199 | 199 | 0 | 75 | 7 | 153 | 153 | 157 | 146 | 60 | 94 | 107 | 206 | 217 | 206 | 128 | 92 | 67 | 0.099259 | Rain
10 |  | Rupam Jyoti Gogoi | Tinsukia | Tinsukia | 9 | 7 | 13 | 0 | 13 | 7 | 225 | 0 | 0 | 0 | 33 | 83 | 7 | 120 | 92 | 37 | 36 | 0 | 85 | 150 | 104 | 115 | 27 | 97 | 56 | 35 | 34 | 38 | 40 | 53 | 48 | 0.21333 | Rain
11 |  | Biprojit Roy | Algapur | Hailakandi | 7 | 7 | 11 | 1 | 10 | 1 | 175 | 54 | 28 | 2 | 25 | 66 | 61 | 60 | 68 | 59 | 69 | 7 | 82 | 76 | 62 | 63 | 75 | 34 | 58 | 98 | 83 | 81 | 71 | 52 | 67 | 0.38286 |  | 10th-May | 5100 | 3782
12 |  | Biprojit Roy | Hailakandi | Hailakandi | 7 | 6 | 7 | 1 | 6 | 1 | 175 | 53 | 55 | 0 | 37 | 33 | 43 | 47 | 55 | 76 | 65 | 15 | 59 | 60 | 29 | 58 | 63 | 13 | 26 | 66 | 64 | 75 | 62 | 81 | 73 | 0.41714 |  | 20th-May | 2955
13 |  | Biprojit Roy | Lala | Hailakandi | 1 | 1 | 2 | 0 | 2 |  | 25 | 21 | 17 | 0 | 4 | 0 | 8 | 2 | 3 | 5 | 4 | 0 | 4 | 5 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 4 | 3 | 3 | 0.12
14 |  | Biprojit Roy | Katlichera | Hailakandi | 7 | 7 | 7 | 0 | 7 | 1 | 175 | 60 | 72 | 0 | 75 | 78 | 96 | 104 | 91 | 105 | 78 | 70 | 97 | 105 | 114 | 92 | 69 | 26 | 59 | 81 | 75 | 88 | 86 | 83 | 77 | 0.44 |  | 15th-May | 4080
15 |  | Biprojit Roy | Badarpur | Shribhumi | 25 | 25 | 61 | 0 | 61 | 2 | 625 | 170 | 159 | 36 | 179 | 290 | 319 | 273 | 287 | 290 | 337 | 83 | 315 | 197 | 212 | 210 | 237 | 145 | 199 | 244 | 292 | 272 | 241 | 201 | 309 | 0.4944 |  | 15th-May | 28470
16 |  | Biprojit Roy | Shribhumi Sadar | Shribhumi | 10 | 8 | 45 | 1 | 44 | 1 | 250 | 14 | 30 | 9 | 10 | 62 | 46 | 63 | 79 | 58 | 34 | 35 | 70 | 44 | 45 | 59 | 46 | 24 | 19 | 23 | 58 | 73 | 62 | 18 | 69 | 0.276 |  | 10th-May | 3630
17 |  | Biprojit Roy | Nilambazar | Shribhumi | 20 | 19 | 65 | 0 | 65 | 3 | 500 | 158 | 148 | 88 | 52 | 41 | 170 | 55 | 108 | 107 | 154 | 88 | 145 | 157 | 110 | 147 | 124 | 22 | 43 | 148 | 95 | 124 | 125 | 90 | 67 | 0.134 |  | 10th-May | 5716
18 |  | Apu Ray | Rk Nagar | Shribhumi | 31 | 26 | 96 | 8 | 88 | 0 | 775 | 95 | 141 | 58 | 164 | 103 | 132 | 125 | 161 | 183 | 181 | 207 | 168 | 188 | 220 | 165 | 217 | 74 | 131 | 216 | 196 | 170 | 209 | 204 | 161 | 0.20774 |  | 15th-May | 13287 | 9683
19 |  | Apu Ray | Patharkandi | Shribhumi | 54 | 48 | 151 | 0 | 151 | 2 | 1350 | 262 | 273 | 36 | 198 | 32 | 152 | 292 | 312 | 365 | 362 | 62 | 396 | 323 | 299 | 310 | 346 | 10 | 133 | 334 | 316 | 314 | 305 | 313 | 279 | 0.20667 |  | 15th-May | 21433 | 12219
20 |  | Utpal Rabha | Chandrapur | Kamrup M | 24 | 24 | 37 | 3 | 34 | 9 | 600 | 143 | 0 | 43 | 18 | 235 | 305 | 269 | 242 | 308 | 179 | 7 | 44 | 28 | 74 | 181 | 227 | 12 | 38 | 304 | 290 | 281 | 220 | 183 | 251 | 0.41833 |  | 10th-May | 20799 | 11600
21 |  | Humayun Kabir | Agomani | Dhubri | 7 | 4 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 55 | 41 | 42 | 44 | 46 | 36 | 33 | 13 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
22 | NC | Humayun Kabir | Baghbar | Barpeta | 3 | 3 | 3 | 0 | 3 | 3 | 75 | 112 | 132 | 10 | 25 | 82 | 58 | 46 | 83 | 53 | 55 | 31 | 95 | 71 | 45 | 55 | 91 | 57 | 89 | 100 | 74 | 97 | 73 | 89 | 76 | 1.0133
23 |  | Tanmoy Dutta | Kampur | Nagaon | 5 | 5 | 6 | 1 | 5 |  | 125 | 93 | 91 | 84 | 118 | 126 | 98 | 133 | 125 | 136 | 128 | 0 | 73 | 123 | 111 | 116 | 124 | 104 | 64 | 60 | 46 | 60 | 33 | 31 | 123 | 0.984
|  |  | Total | [7 empty] | 8625 | 1592 | 1719 | 875 | 1923 | 3042 | 3059 | 3032 | 3414 | 2047 | 2875 | 894 | 3091 | 2384 | 2861 | 2764 | 2244 | 1776 | 2083 | 2984 | 2781 | 3031 | 2850 | 2624 | 1934 | 0.22423

## FC_Performance Matrix-July-25
1st - 29th Aug Coordinator Progress Report
Co-ordinator Name | Survey Areas | District Name | Surveyor Deployed | Active Surveyor | Dag per Surveyor | Target Dag | 2025-08-01 | 2025-08-02 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-11 | 2025-08-12 | 13th-Aug | 14th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | % of 26th-Aug Achieved Dags | 27th-Aug | 28th-Aug | 29th-Aug | % of 29th-Aug Achieved Dags
Dibakar Kalita | Reservey/Naksha | Golaghat | 29 | 20 | 20&25 | 160 | 66 | 163 | 142 | 236 | 238 | 332 | 254 | 223 | 269 | 232 | 172 | 254 | 194 | 224 | 241 | 207 | 210 | 0 | 78 | 0.4875 | 113 | 85 | 102 | 0.6375
Tanmoy Dutta | Naksha/NC | Nagaon/Hojai | 36 | 35 | 20&25 | 770 | 93 | 140 | 91 | 244 | 537 | 613 | 616 | 287 | 532 | 508 | 0 | 531 | 316 | 266 | 130 | 73 | 150 | 158 | 370 | 0.48052 | 324 | 331 | 452 | 0.58701
Utpal Rabha | Reservey | Kamrup M | 24 | 22 | 25 | 720 | 143 | 0 | 43 | 18 | 235 | 305 | 269 | 242 | 308 | 179 | 7 | 44 | 181 | 227 | 12 | 38 | 304 | 290 | 281 | 0.39028 | 220 | 183 | 251 | 0.34861
Biprojit Roy | Reservey | Shribhumi/Hailakandi | 78 | 68 | 25 | 1925 | 530 | 509 | 135 | 382 | 570 | 743 | 604 | 691 | 700 | 741 | 298 | 772 | 637 | 617 | 242 | 404 | 668 | 675 | 721 | 0.37455 | 651 | 528 | 665 | 0.34545
Humayun Kabir | Reservey/Naksha/NC | Bongaigaon/Nalbari/Barpeta/Dhubri | 69 | 61 | 20&25 | 1415 | 167 | 321 | 16 | 152 | 432 | 554 | 520 | 350 | 450 | 161 | 44 | 378 | 308 | 405 | 205 | 198 | 250 | 196 | 480 | 0.33922 | 471 | 543 | 425 | 0.30035
Apu Ray | Reservey | Shribhumi | 85 | 81 | 25 | 2125 | 357 | 414 | 94 | 362 | 135 | 284 | 417 | 473 | 548 | 543 | 269 | 564 | 475 | 563 | 84 | 264 | 550 | 512 | 484 | 0.22776 | 514 | 517 | 440 | 0.20706
Rupam Jyoti Gogoi | Reservey/Naksha | Dibrugarh/Tinsukia/Sivsagar | 76 | 76 | 25 | 2400 | 40 | 68 | 34 | 229 | 676 | 621 | 658 | 637 | 37 | 218 | 11 | 556 | 586 | 234 | 463 | 453 | 509 | 720 | 763 | 0.31792 | 758 | 779 | 379 | 0.15792
Ram Kumar Doley | Reservey | Dibrugarh | 55 | 46 | 25 | 1375 | 0 | 181 | 104 | 320 | 593 | 492 | 463 | 463 | 0 | 328 | 0 | 515 | 542 | 214 | 517 | 564 | 583 | 464 | 625 | 0.45455 | 561 | 497 | 0 | 0
Pradip Saikia | NC Forest Reservey | Dhemaji | 29 | 26 | 25 | 0 | 251 | 194 | 210 | 241 | 390 | 149 | 175 | 431 | 55 | 425 | 93 | 306 | 31 | 16 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project-Overview
Present Status |  | Work in Progress
Item | Details | Activity | Status
Survey Completed (NC Villages) | 531 villages | Re-Survey Operations | Ongoing in 926 villages across 6 districts
Survey Completed (NC Forest Villages) | 64 villages
Total Property Details (NAKSHA) | 251067 | NC Survey Operations | Ongoing in 6 villages
Properties Surveyed (NAKSHA Project) | 88153 | NAKSHA Survey Operations | Active in 35 wards
Pending Property Details | 162914
ULBs Covered Under NAKSHA | 10 ULBs (Total Wards: 155)
Wards Completed Under NAKSHA | 117 Wards
Property Completion-Naksha |  | Reservey Villages Details | Count
Properties Completed - Nagaon | 16904 (51074) | Total Villages (Resurvey) | 926
Properties Completed - Hojai | 5633 (16741) | Villages Completed(Reservey) | 36
Properties Completed - Barpeta Road | 9014 (19767) | Villages in Data Verification Process | 58
Properties Completed - Bongaigaon | 12748 (41125) | Ongoing Villages | 287
Properties Completed - Abhayapuri | 5816 (7987)
Properties Completed - Nalbari | 9056 (35835)
Properties Completed - Mangaldoi | 4559 (21648) | Field Coordinator | Active Villages | Below 50% Completion | Above 50% Completion | Above 80% Completion | Almost Completed
Properties Completed - Dhekiajuli | 8976 (16725) | Apu Ray | 59 | 29 | 18 | 5 | 7
Properties Completed - Sivasagar | 10343 (19485) | Biprojit Roy | 72 | 0 | 53 | 12 | 7
Properties Completed - Golaghat | 4988 (20678) | Rupam Gogoi | 69 | 29 | 33 | 7 | 0
Re-Survey Villages Completed |  | Raam Doley | 51 | 21 | 22 | 0 | 8
Re-Survey Villages Completed | 37 villages | Utpal Rabha | 14 | 11 | 3 | 0 | 5
Re-Survey Circles Covered | Dibrugarh West, Chandrapur, Chabua,Kampur,Moran,algapur,sadar,algapur,Hailakandi | Pradip Saikia | 0 | 0 | 0 | 0 | 0
HRs Details |  | Dibakar Kalita | 19 | 8 | 11
Active Teams | 551
HRs in Survey/Re-Survey | 384
HRs in NC Survey | 6
HRs in NAKSHA | 161
Additional HRs Ready to Deploy | 49
Assistant Surveyors at Worksites | 551
Re-Survey Work Issues |  | NAKSHA Project Issues
Problem Area | Description | Problem Area | Description
Network Connectivity | Non-availability in remote areas | Municipality Coordination | Lack of presence of Municipality Member/Text Collector delays verification
HR Challenges | Public reluctance, lack of cooperation | Multiple Site Visits | Owners unaware of survey schedule, leading to repeated site visits
Device Problems | CORS ID auth issues, Trimble malfunctions | Surveyor Access Restrictions | Owners allow survey only when accompanied by a Municipality Member
Vehicle Issues | Breakdowns and transport unavailability | Data Synchronization | Network issues causing delays
Weather Challenges | Heavy rain, extreme heat hampering field work | Property Owner Availability | Unavailable during visits, slowing verification
|  | Public Awareness | Lack of understanding causing resistance/misinformation
|  | Weather & Logistics | Rains, heat, transport issues

## Less than 16 Dags
SURVEYOR COLLECTED LESS THEN 16 DAG ON 29th-Aug
Sl No | Field Coordinator | Name of the Hired Surveyor | Batch No | Circle Name | District Name | Dag
1 | BIPROJIT ROY | Robiul Hussain | Batch 2 | Badarpur | Karimganj | 5
2 | BIPROJIT ROY | Koyes Ahmed Barbuiya | Batch 3 | Algapur | Hailakandi | 14 | Today present 473
3 | BIPROJIT ROY | Pradip Riang | Batch 3 | Algapur | Hailakandi | 5 | 0 dag - 253
4 | UTPAL RABHA | Suju Kr Gayari | Batch 3 | Chandrapur | Kamrup M | 6 | 1 to 5 - 43
5 | BIPROJIT ROY | Suman Malakar | Batch 4 | Lala | Hailakandi | 3 | 6 to 15 - 119
6 | APU RAY | Arup Goswami | Batch 4 | Patharkandi | Karimganj | 11 | 16 or greater - 58
7 | BIPROJIT ROY | Annu Arddao | Batch 4 | Shribhumi Sadar | Karimganj | 4
8 | APU RAY | Jyotisman Deka | Batch 4 | Patharkandi | Karimganj | 9 | Total rover used - 164
9 | UTPAL RABHA | Ripunjoy Deka | Batch 4 | Chandrapur | Kamrup M | 7 | Total points collected - 9146
10 | APU RAY | Rezanuj Zaman | Batch 5 | Patharkandi | Karimganj | 4 | Total surveyor present - 340
11 | BIPROJIT ROY | Surojit Daulagupu | Batch 5 | Shribhumi Sadar | Karimganj | 11 | Surveyors collected more than 50 points - 83
12 | BIPROJIT ROY | Josmaidao Thaosen | Batch 5 | Shribhumi Sadar | Karimganj | 12 | % of Surveyors collect more than 50 points today - 24.41
13 | BIPROJIT ROY | Lasmi Debragede | Batch 5 | Shribhumi Sadar | Karimganj | 7
14 | BIPROJIT ROY | Rahul Langthasa | Batch 5 | Shribhumi Sadar | Karimganj | 7
15 | APU RAY | Sohamdao Naiding | Batch 5 | Patharkandi | Karimganj | 3
16 | BIPROJIT ROY | Sunabi Johori | Batch 5 | Shribhumi Sadar | Karimganj | 5
17 | APU RAY | Kamal Rajbongshi | Batch 5 | Patharkandi | Karimganj | 5
18 | APU RAY | Sanjoy Shyam | Batch 5 | Patharkandi | Karimganj | 6
19 | UTPAL RABHA | Abdul Mazid Mondal | Batch 6 | Chandrapur | Kamrup M | 12
20 | APU RAY | Deep Jyoti Sarania | Batch 6 | Patharkandi | Karimganj | 7
21 | UTPAL RABHA | Prasenjit Barman | Batch 6 | Chandrapur | Kamrup M | 11
22 | BIPROJIT ROY | Samsul Hoque | Batch 6 | Badarpur | Karimganj | 10
23 | BIPROJIT ROY | Nur Alom Sheikh | Batch 6 | Badarpur | Karimganj | 7
24 | BIPROJIT ROY | Altaf Hussain Barbhuiyan | Batch 6 | Katlichera | Hailakandi | 13
25 | APU RAY | Azmal Hussain Choudhury | Batch 6 | RK nagar | Karimganj | 7
26 | APU RAY | Dhrubojyoti Roy | Batch 6 | RK nagar | Karimganj | 10
27 | UTPAL RABHA | Rituparna Saikia | Batch 6 | Chandrapur | Kamrup M | 14
28 | BIPROJIT ROY | Abdul Maleque | Batch 6 | Badarpur | Karimganj | 10
29 | BIPROJIT ROY | Ashan Ali | Batch 6 | Badarpur | Karimganj | 12
30 | BIPROJIT ROY | Hasen Ali | Batch 6 | Badarpur | Karimganj | 10
31 | APU RAY | Nayanjyoti kalita | Batch 6 | Patharkandi | Karimganj | 8
32 | APU RAY | Eunus Ali | Batch 6 | Patharkandi | Karimganj | 2
33 | APU RAY | Hemonto Paw | Batch 6 | Patharkandi | Karimganj | 4
34 | APU RAY | Hirak Jyoti Sarania | Batch 7 | Patharkandi | Karimganj | 11
35 | APU RAY | Chiraj Morang | Batch 7 | Patharkandi | Karimganj | 14
36 | BIPROJIT ROY | Mridul Boruah | Batch 8 | Badarpur | Karimganj | 11
37 | BIPROJIT ROY | Noba Basumatary | Batch 8 | Nilambazar | Karimganj | 5
38 | BIPROJIT ROY | Abul Hussain | Batch 8 | Badarpur | Karimganj | 12
39 | RUPAM JYOTI GOGOI | Bhaben Chutia | Batch 8 | Dibrugarh East | Dibrugarh | 5
40 | RUPAM JYOTI GOGOI | Mridupaban Gogoi | Batch 8 | Dibrugarh East | Dibrugarh | 13
41 | APU RAY | Gunindra Deuri | Batch 8 | Patharkandi | Karimganj | 4
42 | RUPAM JYOTI GOGOI | Kapil Dev Brahma | Batch 8 | Dibrugarh East | Dibrugarh | 3
43 | RUPAM JYOTI GOGOI | Durgeswar Pegu | Batch 9 | Dibrugarh East | Dibrugarh | 3
44 | APU RAY | Rohan Sahariah | Batch 9 | Patharkandi | Karimganj | 4
45 | APU RAY | Tarik Ahmed | Batch 9 | Patharkandi | Karimganj | 4
46 | RUPAM JYOTI GOGOI | Bishwawanti Sonowal | Batch 9 | Tinsukia | Tinsukia | 2
47 | BIPROJIT ROY | Bitu Buragohain | Batch 10 | Badarpur | Karimganj | 11
48 | APU RAY | Karishma Ahmed | Batch 10/Batch 11 | Patharkandi | Karimganj | 9
49 | BIPROJIT ROY | Debajyoti Gogoi | Batch 10 | Badarpur | Karimganj | 5
50 |  | Abhijit Deori | Batch 10 | Moran | Dibrugarh | 14
51 | BIPROJIT ROY | Palash Chutia | Batch 10 | Badarpur | Karimganj | 13
52 | UTPAL RABHA | Md Abdus Salam | Batch 10 | Chandrapur | Kamrup M | 14
53 | APU RAY | Sulaiman Ali | Batch 10 | Patharkandi | Karimganj | 4
54 | RUPAM JYOTI GOGOI | Poonam Barman | Batch 11 | Tinsukia | Tinsukia | 5
55 | BIPROJIT ROY | Bibek Goutam | Batch 11 | Badarpur | Karimganj | 2
56 | APU RAY | Nurjahan Begum | Batch 12 | Patharkandi | Karimganj | 3
57 | APU RAY | Sopikul Hoque | Batch 12 | Patharkandi | Karimganj | 5
58 | BIPROJIT ROY | Abdul Motin Ansary | Batch 12 | Badarpur | Karimganj | 12
59 | BIPROJIT ROY | Abdul Wahab | Batch 12 | Badarpur | Karimganj | 6
60 | APU RAY | Gofiur Rahman | Batch 12 | Patharkandi | Karimganj | 5
61 | APU RAY | Tafazul Haque | Batch 12 | Patharkandi | Karimganj | 3
62 | APU RAY | Bhrigu Das | Batch 12 | Patharkandi | Karimganj | 11
63 | RUPAM JYOTI GOGOI | Mokibul Islam | Batch 12 | chabua | Dibrugarh | 10
64 | BIPROJIT ROY | Mohir Uddin | Batch 12 | Badarpur | Karimganj | 7
65 | BIPROJIT ROY | Sumesh Ali | Batch 12 | Badarpur | Karimganj | 9
66 | APU RAY | Hazrat Ali Rezza | BATCH 13 | Patharkandi | Karimganj | 3
67 |  | Jalaluddin Ahmed | BATCH 13 | moran | Dibrugarh | 7
68 | BIPROJIT ROY | Jiaur Rahman Laskar | BATCH 13 | Hailakandi | Hailakandi | 4
69 |  | Majad Ali | BATCH 13 | moran | Dibrugarh | 9
70 | BIPROJIT ROY | Mirjan Ahmed Laskar | BATCH 13 | Algapur | Hailakandi | 9
71 |  | Priyanka Hazarika | BATCH 13 | moran | Dibrugarh | 10
72 |  | Rupali Nath | BATCH 13 | Moran | Dibrugarh | 10
73 |  | Saddam Hussain | BATCH 13 | moran | Dibrugarh | 12
74 |  | Samidul Islam | BATCH 13 | moran | Dibrugarh | 13
75 |  | Sher Golam Rabbani | BATCH 13 | moran | Dibrugarh | 10
76 | RUPAM JYOTI GOGOI | Shimangshu Baruah | BATCH 13 | Tinsukia | Tinsukia | 7
77 |  | Sirajul Hoque | BATCH 13 | Moran | Dibrugarh | 9
78 | BIPROJIT ROY | Tayabur Rahaman Mazumder | BATCH 13 | Katlichera | Hailakandi | 10
79 | APU RAY | Sumon Kundu | BATCH 13 | RK nagar | Karimganj | 14
80 | APU RAY | Laku Das | BATCH 6 | Patharkandi | Karimganj | 2
81 | RUPAM JYOTI GOGOI | Jitul doley | Batch 7 | tinsukia | TINSUKIA | 12
82 | RUPAM JYOTI GOGOI | Manjil Payeng | Batch 9 | tinsukia | TINSUKIA | 12
83 | RUPAM JYOTI GOGOI | Anamika buragohain | Batch 5 | tinsukia | TINSUKIA | 10
84 | APU RAY | Bikash Singha | Batch 14 | Patharkandi | Karimganj | 8
85 | APU RAY | Furkan Ahmed | Batch 14 | Patharkandi | Karimganj | 5
86 | APU RAY | H. Debit Singha | Batch 14 | Patharkandi | Karimganj | 7
87 | APU RAY | Ijaj Ahmed Laskar | Batch 14 | Patharkandi | Karimganj | 5
88 | APU RAY | K. Priyojit Singha | Batch 14 | Patharkandi | Karimganj | 8
89 | APU RAY | Mabrur Ahmed Barbhuiya | Batch 14 | Patharkandi | Karimganj | 10
90 | APU RAY | Probhakar Das | Batch 14 | Patharkandi | Karimganj | 4
91 | APU RAY | Santosh Kumar Kanu | Batch 14 | Patharkandi | Karimganj | 5
92 | APU RAY | Sh Roshan Singha | Batch 14 | Patharkandi | Karimganj | 7
93 | APU RAY | T Nganthoiba Singfha | Batch 14 | Patharkandi | Karimganj | 6
94 | APU RAY | Tinki Nag | Batch 14 | Patharkandi | Karimganj | 7
95 | APU RAY | Sirajul Abedin Choudhury | Batch 15 | Patharkandi | Karimganj | 4
96 | APU RAY | Debangli Das | Batch 14 | Patharkandi | Karimganj | 4
97 | APU RAY | Dabit Singha | Batch 14 | Patharkandi | Karimganj | 5
98 | BIPROJIT ROY | A S Imdadur Rahman | Batch 15 | Nilambazar | Karimganj | 10
99 | APU RAY | Susmita Rani Das | Batch 15 | Patharkandi | Karimganj | 3
100 | APU RAY | L. Bikram Singha | Batch 14 | Patharkandi | Karimganj | 5
101 | BIPROJIT ROY | Shibom Chakraborty | Batch 14 | Nilambazar | Karimganj | 14
102 | BIPROJIT ROY | Shakir Chodhury | Batch 15 | Nilambazar | Karimganj | 4
103 | BIPROJIT ROY | Sultan Ahmed | Batch 14 | Nilambazar | Karimganj | 5
104 | APU RAY | Suresh Kumar Singha | Batch 14 | Patharkandi | Karimganj | 6
105 | BIPROJIT ROY | Gulzar Hussain | Batch 15 | Nilambazar | Karimganj | 10
106 | BIPROJIT ROY | Juber Ahmed | Batch 14 | Nilambazar | Karimganj | 6
107 | BIPROJIT ROY | Drishti Dey | Batch 15 | Nilambazar | Karimganj | 8
108 | APU RAY | Md Jabir Hussain | Batch 14 | RK nagar | Karimganj | 10
109 | APU RAY | Raja Iqbal | Batch 15 | RK nagar | Karimganj | 10
110 | APU RAY | Abdul Ahad | Batch 15 | RK nagar | Karimganj | 7
111 | BIPROJIT ROY | Prabal Chakraborty | Batch 15 | Nilambazar | Karimganj | 5
112 | BIPROJIT ROY | Debosree Dhar | Batch 14 | Katlichera | Hailakandi | 11
113 | BIPROJIT ROY | H. Roshan Singha | Batch 14 | Hailakandi | Hailakandi | 12
114 | BIPROJIT ROY | Abu Saleh Ubaidulla Barbhuiya | Batch 15 | Katlichera | Hailakandi | 11
115 | BIPROJIT ROY | Aksor Ahmed Choudhury | Batch 15 | Algapur | Hailakandi | 9
116 | UTPAL RABHA | Biki Boro | Batch 15 | Chandrapur | Kamrup M | 10
117 | HUMAYUN KABIR | Jonmejoy Hajowary | Batch 3 | BONGAIGAON | BONGAIGAON | 3
118 | HUMAYUN KABIR | Sontosh Ali | Batch 3 | BONGAIGAON | BONGAIGAON | 9
119 | HUMAYUN KABIR | Saiful Islam | Batch 3 | BARNAGAR | BARPETA | 11
120 | SADULLA HUSSAIN | Abhijit Thakuria | Batch 3 | NALBARI | NALBARI | 10
121 | SADULLA HUSSAIN | Jeherul Islam | Batch 3 | NALBARI | NALBARI | 10
122 | SADULLA HUSSAIN | Mohijul Hoque | Batch 3 | NALBARI | NALBARI | 13
123 | SADULLA HUSSAIN | Niran Kathar | Batch 3 | NALBARI | NALBARI | 10
124 | SADULLA HUSSAIN | Saidul Hoque | Batch 3 | NALBARI | NALBARI | 12
125 |  | Subhra Jyoti Baruah | Batch 4 | GOLAGHAT | GOLAGHAT | 14
126 | HUMAYUN KABIR | Meherul Islam | Batch 4 | BONGAIGAON | BONGAIGAON | 5
127 | HUMAYUN KABIR | Rejaul Karim | Batch 4 | BONGAIGAON | BONGAIGAON | 7
128 | SADULLA HUSSAIN | Dhrubajyoti Barman | Batch 4 | NALBARI | NALBARI | 10
129 | SADULLA HUSSAIN | Hasimuddin Choudhury | Batch 4 | NALBARI | NALBARI | 10
130 | SADULLA HUSSAIN | Islam Ali | Batch 4 | NALBARI | NALBARI | 10
131 | SADULLA HUSSAIN | Kishor Haloi | Batch 4 | NALBARI | NALBARI | 12
132 | HUMAYUN KABIR | Imar Ali | Batch 4 | BARNAGAR | BARPETA | 14
133 | SADULLA HUSSAIN | Jamir Uddin | Batch 5 | NALBARI | NALBARI | 7
134 | SADULLA HUSSAIN | Mostafizur rohman | Batch 5 | NALBARI | NALBARI | 8
135 | SADULLA HUSSAIN | Haidar Ali | Batch 5 | NALBARI | NALBARI | 10
136 | SADULLA HUSSAIN | Ijajul Haque | Batch 5 | NALBARI | NALBARI | 8
137 | SADULLA HUSSAIN | Nurul Islam Choudhury | Batch 5 | NALBARI | NALBARI | 8
138 | KUNAL HAZARIKA | Sanjib Bharali | Batch 6 | Mangaldoi | DARRANG | 8
139 | TANMOY DUTTA | Biswajit Borah | Batch 5 | KAMPUR | NAGAON | 12
140 | TANMOY DUTTA | Akabbar Ali | BATCH 13 | KAMPUR | NAGAON | 11
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200