## Naksha
Naksha Progress Report
District | Name ULB/Town/ City | Circle | Coordinator Name | Active Surveyors | Daily KPI | 1st-Aug | 2nd-Aug | 4th-Aug | 5th-Aug | 6th-Aug | 7th-Aug | 8th-Aug | 9th-Aug | 11th-Aug | 12th-Aug | 13th-Aug | 14th-Aug | 16th-Aug | 18th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | 27th-Aug | % of 27th-Aug | Total Wards | Running Wards | Total Ward Completed | Pending ward | Completion Date
Bongaigaon | Abhayapuri | Srijangram | Humayun Kabir | 12 | 240 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0 |  | 11 | 0 | 11 | 0
Sonitpur | Dhekiajuli MB | Dhekiajuli | Kunal Hazarika | 9 | 180 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0 |  | 10 | 0 | 10 | 0
Darrang | Mangaldoi MB | Mangaldoi | Kunal Hazarika | 2 | 40 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0 |  | 10 | 0 | 10 | 0
Sivasagar | Sivasagar MB | Sivasagar | Rupam Gogoi | 10 | 200 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0 |  | 14 | 0 | 14 | 0
Barpeta | Barpeta Road | Barnagar | Humayun Kabir | 8 | 160 | 53 | 92 | 6 | 72 | 100 | 116 | 110 | 146 | 112 | 23 | 0 | 114 | 53 | 97 | 118 | 124 | 82 | 82 | 20 | 10 | 103 | 98 | 0.6125 | 10 | 5 | 5 | 0 | 20th-Auguest | 31st-July
Bongaigaon | Bongaigaon | Bongaigaon | Humayun Kabir | 14 | 280 | 0 | 62 | 0 | 0 | 76 | 111 | 100 | 75 | 36 | 50 | 0 | 169 | 57 | 52 | 71 | 103 | 66 | 27 | 130 | 112 | 76 | 86 | 0.30714 | 25 | 1 | 24 | 0 | 16th-Auguest | 31st-July
Golaghat | Golaghat MB | Golaghat | Dibakar Kalita | 8 | 160 | 0 | 33 | 7 | 63 | 44 | 65 | 31 | 0 | 95 | 118 | 0 | 88 | 0 | 18 | 33 | 63 | 0 | 0 | 0 | 0 | 78 | 113 | 0.70625 | 13 | 6 | 6 | 1 | 30th-October
Hojai | Hojai MB | Hojai | Tonmoy Dutta | 11 | 220 | 0 | 49 | 7 | 112 | 123 | 191 | 197 | 162 | 154 | 130 | 0 | 121 | 48 | 53 | 65 | 90 | 26 | 9 | 90 | 112 | 61 | 14 | 0.063636 | 19 | 1 | 18 | 0 | 30th-September
Nalbari | Nalbari MB | Nalbari | Humayun Kabir | 27 | 540 | 0 | 35 | 0 | 0 | 133 | 227 | 220 | 0 | 213 | 0 | 0 | 0 | 99 | 0 | 64 | 87 | 0 | 0 | 0 | 0 | 204 | 214 | 0.3963 | 17 | 11 | 6 | 0 | 18th-September
Nagaon | Nagaon MB | Nagaon | Tonmoy Dutta | 22 | 440 | 0 | 0 | 0 | 14 | 289 | 324 | 286 | 0 | 242 | 250 | 0 | 337 | 322 | 246 | 135 | 52 | 0 | 0 | 0 | 0 | 249 | 277 | 0.62955 | 26 | 12 | 11 | 3 | 12th-October
[5 empty] | 1800 | 27th-Aug: 802

## Reservey
Reservey Progress report
Sl No | Survey Areas | Co-ordinator | Circle Name | District Name | Surveyor Deployed | Active Surveyor | Total Villages | Village Completed | Pending Villages | Data Verification | Daily KPI | 1st-Aug | 2nd-Aug | 4th-Aug | 5th-Aug | 6th-Aug | 7th-Aug | 8th-Aug | 9th-Aug | 11th-Aug | 12th-Aug | 13th-Aug | 14th-Aug | 16th-Aug | 18th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | 27th-Aug | % of 27th-Aug | Remarks | Start Date | No of Polygon | Completed Polygon Till Date | End date
1 | NC Forest Reservey | Pradip Saikia | Dhemaji | Dhemaji | 6 | 0 | 8 | 8 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
2 |  | Pradip Saikia | Gogamukh | Dhemaji | 15 | 15 | 18 | 10 | 8 |  | 0 | 164 | 194 | 159 | 241 | 237 | 149 | 77 | 313 | 55 | 338 | 93 | 190 | 253 | 183 | 31 | 16 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
3 |  | Pradip Saikia | Jonai | Dhemaji | 9 | 7 | 22 | 9 | 13 |  | 0 | 87 | 0 | 51 | 0 | 153 | 0 | 98 | 118 | 0 | 87 | 0 | 116 | 8 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
4 |  | Pradip Saikia | Sissiborgaon | Dhemaji | 7 | 7 | 10 | 10 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
5 | Reservey | Ram Kumar Doley | Dibrugarh West | Dibrugarh | 55 | 51 | 169 | 17 | 152 | 5 | 1375 | 0 | 181 | 104 | 320 | 593 | 492 | 463 | 463 | 0 | 328 | 0 | 515 | 397 | 531 | 542 | 214 | 517 | 564 | 583 | 464 | 625 | 561 | 0.408
6 |  | Rupam Jyoti Gogoi | Dibrugarh East | Dibrugarh | 37 | 31 | 116 | 0 | 116 | 9 | 925 | 40 | 48 | 34 | 184 | 333 | 279 | 339 | 346 | 0 | 218 | 4 | 318 | 46 | 314 | 325 | 147 | 272 | 290 | 268 | 263 | 300 | 422 | 0.45622
7 |  | Rupam Jyoti Gogoi | Moran | Dibrugarh | 23 | 18 | 60 | 2 | 57 |  | 575 | 66 | 130 | 135 | 173 | 194 | 267 | 223 | 223 | 174 | 114 | 172 | 166 | 0 | 82 | 141 | 161 | 241 | 207 | 210 | 206 | 219 | 208 | 0.36174
8 |  | Rupam Jyoti Gogoi | Chabua | Dibrugarh | 27 | 23 | 104 | 2 | 102 | 7 | 675 | 0 | 20 | 26 | 12 | 260 | 335 | 199 | 199 | 0 | 75 | 7 | 153 | 153 | 157 | 146 | 60 | 94 | 107 | 206 | 217 | 206 | 128 | 0.18963
10 |  | Rupam Jyoti Gogoi | Tinsukia | Tinsukia | 9 | 7 | 13 | 0 | 13 | 7 | 225 | 0 | 0 | 0 | 33 | 83 | 7 | 120 | 92 | 37 | 36 | 0 | 85 | 150 | 104 | 115 | 27 | 97 | 56 | 35 | 34 | 38 | 40 | 0.17778
11 |  | Biprojit Roy | Algapur | Hailakandi | 7 | 7 | 11 | 1 | 10 | 1 | 175 | 54 | 28 | 2 | 25 | 66 | 61 | 60 | 68 | 59 | 69 | 7 | 82 | 76 | 62 | 63 | 75 | 34 | 58 | 98 | 83 | 81 | 71 | 0.40571 |  | 10th-May | 5100 | 3782
12 |  | Biprojit Roy | Hailakandi | Hailakandi | 7 | 6 | 7 | 1 | 6 | 1 | 175 | 53 | 55 | 0 | 37 | 33 | 43 | 47 | 55 | 76 | 65 | 15 | 59 | 60 | 29 | 58 | 63 | 13 | 26 | 66 | 64 | 75 | 62 | 0.35429 |  | 20th-May | 2955
13 |  | Biprojit Roy | Lala | Hailakandi | 1 | 1 | 2 | 0 | 2 |  | 25 | 21 | 17 | 0 | 4 | 0 | 8 | 2 | 3 | 5 | 4 | 0 | 4 | 5 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 4 | 0.16
14 |  | Biprojit Roy | Katlichera | Hailakandi | 7 | 6 | 7 | 0 | 7 | 1 | 175 | 60 | 72 | 0 | 75 | 78 | 96 | 104 | 91 | 105 | 78 | 70 | 97 | 105 | 114 | 92 | 69 | 26 | 59 | 81 | 75 | 88 | 86 | 0.49143 |  | 15th-May | 4080
15 |  | Biprojit Roy | Badarpur | Shribhumi | 25 | 22 | 61 | 0 | 61 | 2 | 625 | 170 | 159 | 36 | 179 | 290 | 319 | 273 | 287 | 290 | 337 | 83 | 315 | 197 | 212 | 210 | 237 | 145 | 199 | 244 | 292 | 272 | 241 | 0.3856 |  | 15th-May | 28470
16 |  | Biprojit Roy | Shribhumi Sadar | Shribhumi | 10 | 8 | 45 | 1 | 44 | 1 | 250 | 14 | 30 | 9 | 10 | 62 | 46 | 63 | 79 | 58 | 34 | 35 | 70 | 44 | 45 | 59 | 46 | 24 | 19 | 23 | 58 | 73 | 62 | 0.248 |  | 10th-May | 3630
17 |  | Biprojit Roy | Nilambazar | Shribhumi | 20 | 19 | 65 | 0 | 65 | 3 | 500 | 158 | 148 | 88 | 52 | 41 | 170 | 55 | 108 | 107 | 154 | 88 | 145 | 157 | 110 | 147 | 124 | 22 | 43 | 148 | 95 | 124 | 125 | 0.25 |  | 10th-May | 5716
18 |  | Apu Ray | Rk Nagar | Shribhumi | 31 | 30 | 96 | 8 | 88 | 0 | 775 | 95 | 141 | 58 | 164 | 103 | 132 | 125 | 161 | 183 | 181 | 207 | 168 | 188 | 220 | 165 | 217 | 74 | 131 | 216 | 196 | 170 | 209 | 0.26968 |  | 15th-May | 13287 | 9683
19 |  | Apu Ray | Patharkandi | Shribhumi | 54 | 45 | 151 | 0 | 151 | 2 | 1350 | 262 | 273 | 36 | 198 | 32 | 152 | 292 | 312 | 365 | 362 | 62 | 396 | 323 | 299 | 310 | 346 | 10 | 133 | 334 | 316 | 314 | 305 | 0.22593 |  | 15th-May | 21433 | 12219
20 |  | Utpal Rabha | Chandrapur | Kamrup M | 24 | 23 | 37 | 3 | 34 | 9 | 600 | 143 | 0 | 43 | 18 | 235 | 305 | 269 | 242 | 308 | 179 | 7 | 44 | 28 | 74 | 181 | 227 | 12 | 38 | 304 | 290 | 281 | 220 | 0.36667 |  | 10th-May | 20799 | 11600
21 |  | Humayun Kabir | Agomani | Dhubri | 7 | 7 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 55 | 41 | 42 | 44 | 46 | 36 | 33 | 13 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | Village Completed
22 | NC | Humayun Kabir | Baghbor | Barpeta | 3 | 2 | 3 | 0 | 3 | 3 | 75 | 112 | 132 | 10 | 25 | 82 | 58 | 46 | 83 | 53 | 55 | 31 | 95 | 71 | 45 | 55 | 91 | 57 | 89 | 100 | 74 | 97 | 73 | 0.97333
23 |  | Tanmoy Dutta | Kampur | Nagaon | 5 | 5 | 6 | 1 | 5 |  | 125 | 93 | 91 | 84 | 118 | 126 | 98 | 133 | 125 | 136 | 128 | 0 | 73 | 123 | 111 | 116 | 124 | 104 | 64 | 60 | 46 | 60 | 33 | 0.264
|  |  | Total | [7 empty] | 8625 | 1592 | 1719 | 875 | 1923 | 3042 | 3059 | 3032 | 3414 | 2047 | 2875 | 894 | 3091 | 2384 | 2861 | 2764 | 2244 | 1776 | 2083 | 2984 | 2781 | 3031 | 2850 | 0.33043

## FC_Performance Matrix-July-25
1st - 27th Aug Coordinator Progress Report
Co-ordinator Name | Survey Areas | District Name | Surveyor Deployed | Active Surveyor | Dag per Surveyor | Target Dag | 2025-08-01 | 2025-08-02 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-11 | 2025-08-12 | 13th-Aug | 14th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | % of 26th-Aug Achieved Dags | 27th-Aug | % of 27th-Aug Achieved Dags
Dibakar Kalita | Reservey/Naksha | Golaghat | 29 | 20 | 20&25 | 160 | 66 | 163 | 142 | 236 | 238 | 332 | 254 | 223 | 269 | 232 | 172 | 254 | 194 | 224 | 241 | 207 | 210 | 0 | 78 | 0.4875 | 113 | 0.70625
Tanmoy Dutta | Naksha/NC | Nagaon/Hojai | 36 | 35 | 20&25 | 770 | 93 | 140 | 91 | 244 | 537 | 613 | 616 | 287 | 532 | 508 | 0 | 531 | 316 | 266 | 130 | 73 | 150 | 158 | 370 | 0.48052 | 324 | 0.42078
Ram Kumar Doley | Reservey | Dibrugarh | 55 | 46 | 25 | 1375 | 0 | 181 | 104 | 320 | 593 | 492 | 463 | 463 | 0 | 328 | 0 | 515 | 542 | 214 | 517 | 564 | 583 | 464 | 625 | 0.45455 | 561 | 0.408
Biprojit Roy | Reservey | Shribhumi/Hailakandi | 78 | 68 | 25 | 1925 | 530 | 509 | 135 | 382 | 570 | 743 | 604 | 691 | 700 | 741 | 298 | 772 | 637 | 617 | 242 | 404 | 668 | 675 | 721 | 0.37455 | 651 | 0.33818
Humayun Kabir | Reservey/Naksha/NC | Bongaigaon/Nalbari/Barpeta/Dhubri | 69 | 61 | 20&25 | 1415 | 167 | 321 | 16 | 152 | 432 | 554 | 520 | 350 | 450 | 161 | 44 | 378 | 308 | 405 | 205 | 198 | 250 | 196 | 480 | 0.33922 | 471 | 0.33286
Rupam Jyoti Gogoi | Reservey/Naksha | Dibrugarh/Tinsukia/Sivsagar | 76 | 76 | 25 | 2400 | 40 | 68 | 34 | 229 | 676 | 621 | 658 | 637 | 37 | 218 | 11 | 556 | 586 | 234 | 463 | 453 | 509 | 720 | 763 | 0.31792 | 758 | 0.31583
Utpal Rabha | Reservey | Kamrup M | 24 | 22 | 25 | 720 | 143 | 0 | 43 | 18 | 235 | 305 | 269 | 242 | 308 | 179 | 7 | 44 | 181 | 227 | 12 | 38 | 304 | 290 | 281 | 0.39028 | 220 | 0.30556
Apu Ray | Reservey | Shribhumi | 85 | 81 | 25 | 2125 | 357 | 414 | 94 | 362 | 135 | 284 | 417 | 473 | 548 | 543 | 269 | 564 | 475 | 563 | 84 | 264 | 550 | 512 | 484 | 0.22776 | 514 | 0.24188
Pradip Saikia | NC Forest Reservey | Dhemaji | 29 | 26 | 25 | 0 | 251 | 194 | 210 | 241 | 390 | 149 | 175 | 431 | 55 | 425 | 93 | 306 | 31 | 16 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project-Overview
Present Status |  | Work in Progress
Item | Details | Activity | Status
Survey Completed (NC Villages) | 531 villages | Re-Survey Operations | Ongoing in 926 villages across 6 districts
Total Property Details (NAKSHA) | 251067 | NC Survey Operations | Ongoing in 6 villages
Properties Surveyed (NAKSHA Project) | 86768 | NAKSHA Survey Operations | Active in 37 wards
Pending Property Details | 164299
ULBs Covered Under NAKSHA | 10 ULBs (Total Wards: 155)
Wards Completed Under NAKSHA | 115 Wards
Property Completion-Naksha |  | Reservey Villages Details | Count
Properties Completed - Nagaon | 16365 (51074) | Total Villages (Resurvey) | 926
Properties Completed - Hojai | 5585 (16741) | Villages Completed(Reservey) | 36
Properties Completed - Barpeta Road | 8872 (19767) | Villages in Data Verification Process | 58
Properties Completed - Bongaigaon | 12580 (41125) | Ongoing Villages | 287
Properties Completed - Abhayapuri | 5816 (7987)
Properties Completed - Nalbari | 8768 (35835)
Properties Completed - Mangaldoi | 4559 (21648) | Field Coordinator | Active Villages | Below 50% Completion | Above 50% Completion | Above 80% Completion | Almost Completed
Properties Completed - Dhekiajuli | 8976 (16725) | Apu Ray | 59 | 29 | 18 | 5 | 7
Properties Completed - Sivasagar | 10343 (19485) | Biprojit Roy | 72 | 0 | 53 | 12 | 7
Properties Completed - Golaghat | 4839 (20678) | Rupam Gogoi | 69 | 29 | 33 | 7 | 0
Re-Survey Villages Completed |  | Raam Doley | 51 | 21 | 22 | 0 | 8
Re-Survey Villages Completed | 36 villages | Utpal Rabha | 14 | 11 | 3 | 0 | 5
Re-Survey Circles Covered | Dibrugarh West, Chandrapur, Chabua,Kampur,Moran,algapur,sadar,algapur,Hailakandi | Pradip Saikia | 0 | 0 | 0 | 0 | 0
HRs Details |  | Dibakar Kalita | 19 | 8 | 11
Active Teams | 551
HRs in Survey/Re-Survey | 384
HRs in NC Survey | 6
HRs in NAKSHA | 161
Additional HRs Ready to Deploy | 49
Assistant Surveyors at Worksites | 551
Re-Survey Work Issues |  | NAKSHA Project Issues
Problem Area | Description | Problem Area | Description
Network Connectivity | Non-availability in remote areas | Municipality Coordination | Lack of presence of Municipality Member/Text Collector delays verification
HR Challenges | Public reluctance, lack of cooperation | Multiple Site Visits | Owners unaware of survey schedule, leading to repeated site visits
Device Problems | CORS ID auth issues, Trimble malfunctions | Surveyor Access Restrictions | Owners allow survey only when accompanied by a Municipality Member
Vehicle Issues | Breakdowns and transport unavailability | Data Synchronization | Network issues causing delays
Weather Challenges | Heavy rain, extreme heat hampering field work | Property Owner Availability | Unavailable during visits, slowing verification
|  | Public Awareness | Lack of understanding causing resistance/misinformation
|  | Weather & Logistics | Rains, heat, transport issues

## Less than 16 Dags
SURVEYOR COLLECTED LESS THEN 16 DAG ON 27th-Aug
Sl No | Field Coordinator | Name of the Hired Surveyor | Batch No | Circle Name | District Name | Dag
1 | RAM DOLEY | Nilutpal Gogoi | Batch 1 | Dibrugarh West | Dibrugarh | 14
2 | RAM DOLEY | Udipta Changmai | Batch 1 | Dibrugarh West | Dibrugarh | 15 | Today present 464
3 | RAM DOLEY | Manakh Jyoti Borgohain | Batch 1 | Dibrugarh West | Dibrugarh | 5 | 0 dag - 180
4 | APU RAY | Shoib Akter Mazumder | Batch 3 | RK nagar | Karimganj | 10 | 1 to 5 - 35
5 | BIPROJIT ROY | Koyes Ahmed Barbuiya | Batch 3 | Algapur | Hailakandi | 14 | 6 to 15 - 156
6 | APU RAY | Novendu Seal | Batch 3 | RK nagar | Karimganj | 14 | 16 or greater - 93
7 | BIPROJIT ROY | Pradip Riang | Batch 3 | Algapur | Hailakandi | 11
8 | BIPROJIT ROY | Basith Ahmed Mazarbhuiya | Batch 3 | Algapur | Hailakandi | 12
9 | UTPAL RABHA | Bidyut Basumatary | Batch 3 | Chandrapur | Kamrup M | 4 | Total rover used - 229
10 | UTPAL RABHA | Apurba Basumatary | Batch 3 | Chandrapur | Kamrup M | 15 | Total points collected - 14910
11 | RAM DOLEY | Xavier Hajowar | Batch 4 | Dibrugarh West | Dibrugarh | 12 | Total surveyor present - 335
12 | RAM DOLEY | Jahangir Hussain | Batch 4 | Dibrugarh West | Dibrugarh | 12 | Surveyors collected more than 50 points - 153
13 | APU RAY | Paramita Acharjee | Batch 4 | RK nagar | Karimganj | 6 | % of Surveyors collect more than 50 points today - 45.67
14 | BIPROJIT ROY | Bayshali Das | Batch 4 | Nilambazar | Karimganj | 15
15 | BIPROJIT ROY | Anupom Sarma | Batch 4 | Algapur | Hailakandi | 15
16 | BIPROJIT ROY | Suman Malakar | Batch 4 | Lala | Hailakandi | 4
17 | UTPAL RABHA | Nayan Jyoti Deka | Batch 4 | Chandrapur | Kamrup M | 10
18 | APU RAY | Arup Goswami | Batch 4 | Patharkandi | Karimganj | 2
19 | BIPROJIT ROY | Annu Arddao | Batch 4 | Shribhumi Sadar | Karimganj | 12
20 | APU RAY | Jyotisman Deka | Batch 4 | Patharkandi | Karimganj | 9
21 | UTPAL RABHA | Ripunjoy Deka | Batch 4 | Chandrapur | Kamrup M | 10
22 | RAM DOLEY | Bipul Das | Batch 5 | Dibrugarh West | Dibrugarh | 10
23 | RAM DOLEY | Khandakar Badarat Jaman | Batch 5 | Dibrugarh West | Dibrugarh | 11
24 | RAM DOLEY | Niranjan Kumar Ray | Batch 5 | Dibrugarh West | Dibrugarh | 12
25 | RAM DOLEY | Swmkwar Daimary | Batch 5 | Dibrugarh West | Dibrugarh | 2
26 | APU RAY | Rezanuj Zaman | Batch 5 | Patharkandi | Karimganj | 2
27 | RAM DOLEY | Archana Roy | Batch 5 | Dibrugarh West | Dibrugarh | 8
28 | RAM DOLEY | Bonashmita Senapoti | Batch 5 | Dibrugarh West | Dibrugarh | 8
29 | BIPROJIT ROY | Surojit Daulagupu | Batch 5 | Shribhumi Sadar | Karimganj | 11
30 | BIPROJIT ROY | Josmaidao Thaosen | Batch 5 | Shribhumi Sadar | Karimganj | 14
31 | UTPAL RABHA | Rumi Baruah | Batch 5 | Chandrapur | Kamrup M | 12
32 | BIPROJIT ROY | Lasmi Debragede | Batch 5 | Shribhumi Sadar | Karimganj | 10
33 | BIPROJIT ROY | Rahul Langthasa | Batch 5 | Shribhumi Sadar | Karimganj | 7
34 | APU RAY | Sohamdao Naiding | Batch 5 | Patharkandi | Karimganj | 2
35 | BIPROJIT ROY | Sunabi Johori | Batch 5 | Shribhumi Sadar | Karimganj | 8
36 | RAM DOLEY | Sanjib Saikia | Batch 5 | Dibrugarh West | Dibrugarh | 12
37 | RAM DOLEY | Napa Pegu | Batch 5 | Dibrugarh West | Dibrugarh | 15
38 | APU RAY | Kamal Rajbongshi | Batch 5 | Patharkandi | Karimganj | 6
39 | APU RAY | Sanjoy Shyam | Batch 5 | Patharkandi | Karimganj | 10
40 | RUPAM JYOTI GOGOI | Madhuri Khakhlari | Batch 5 | Dibrugarh East | Dibrugarh | 14
41 | UTPAL RABHA | Abdul Sarwer Mintu | Batch 6 | Chandrapur | Kamrup M | 7
42 | APU RAY | Deep Jyoti Sarania | Batch 6 | Patharkandi | Karimganj | 14
43 | UTPAL RABHA | Prasenjit Barman | Batch 6 | Chandrapur | Kamrup M | 13
44 | BIPROJIT ROY | Samsul Hoque | Batch 6 | Badarpur | Karimganj | 10
45 | BIPROJIT ROY | Nur Alom Sheikh | Batch 6 | Badarpur | Karimganj | 8
46 | BIPROJIT ROY | Altaf Hussain Barbhuiyan | Batch 6 | Katlichera | Hailakandi | 9
47 | APU RAY | Azmal Hussain Choudhury | Batch 6 | RK nagar | Karimganj | 10
48 | APU RAY | Dhrubojyoti Roy | Batch 6 | RK nagar | Karimganj | 10
49 | APU RAY | Sujata Das | Batch 6 | RK nagar | Karimganj | 13
50 | BIPROJIT ROY | Soma Nath | Batch 6 | Hailakandi | Hailakandi | 12
51 | UTPAL RABHA | Rituparna Saikia | Batch 6 | Chandrapur | Kamrup M | 15
52 | BIPROJIT ROY | Abdul Maleque | Batch 6 | Badarpur | Karimganj | 14
53 | BIPROJIT ROY | Ashan Ali | Batch 6 | Badarpur | Karimganj | 12
54 | APU RAY | Nayanjyoti kalita | Batch 6 | Patharkandi | Karimganj | 15
55 | APU RAY | Imran Hussain | Batch 6 | Patharkandi | Karimganj | 2
56 | RAM DOLEY | Atabar Ali | Batch 6 | Dibrugarh West | Dibrugarh | 3
57 | APU RAY | Hemonto Paw | Batch 6 | Patharkandi | Karimganj | 10
58 | APU RAY | Rajdeep Das | Batch 7 | RK nagar | Karimganj | 5
59 | RAM DOLEY | Kangkan Saharia | Batch 7 | Dibrugarh West | Dibrugarh | 5
60 | RAM DOLEY | Kukil Gogoi | Batch 7 | Dibrugarh West | Dibrugarh | 3
61 | RAM DOLEY | Anuradha Saikia | Batch 7 | Dibrugarh West | Dibrugarh | 5
62 | APU RAY | Hirak Jyoti Sarania | Batch 7 | Patharkandi | Karimganj | 12
63 | RUPAM JYOTI GOGOI | Bulbul Borah | Batch 7 | Dibrugarh East | Dibrugarh | 10
64 | RUPAM JYOTI GOGOI | Karan Boruah | Batch 7 | Dibrugarh East | Dibrugarh | 15
65 | RUPAM JYOTI GOGOI | Manidhar Pegu | Batch 7 | Dibrugarh East | Dibrugarh | 12
66 | RAM DOLEY | Dharamjit Pegu | Batch 7 | Dibrugarh West | Dibrugarh | 13
67 | APU RAY | Sukanta Das | Batch 8 | RK nagar | Karimganj | 15
68 | RUPAM JYOTI GOGOI | Luminous Brahma | Batch 8 | Dibrugarh East | Dibrugarh | 9
69 | BIPROJIT ROY | Mridul Boruah | Batch 8 | Badarpur | Karimganj | 13
70 | RAM DOLEY | Anirban Saikia | Batch 8 | Dibrugarh West | Dibrugarh | 15
71 | BIPROJIT ROY | Nabajyoti Kalita | Batch 8 | Badarpur | Karimganj | 9
72 | UTPAL RABHA | Swapnali Baruah | Batch 8 | Chandrapur | Kamrup M | 3
73 | RUPAM JYOTI GOGOI | Madhab Saikia | Batch 8 | Dibrugarh East | Dibrugarh | 13
74 | RUPAM JYOTI GOGOI | Bhaben Chutia | Batch 8 | Dibrugarh East | Dibrugarh | 13
75 | RUPAM JYOTI GOGOI | Mridupaban Gogoi | Batch 8 | Dibrugarh East | Dibrugarh | 14
76 | APU RAY | Gunindra Deuri | Batch 8 | Patharkandi | Karimganj | 4
77 | RUPAM JYOTI GOGOI | Bhabesh Taid | Batch 9 | Dibrugarh East | Dibrugarh | 10
78 | APU RAY | Amar Jyoti Baruah | Batch 9 | Patharkandi | Karimganj | 5
79 | BIPROJIT ROY | Ataur Rahman | Batch 9 | Badarpur | Karimganj | 10
80 | APU RAY | Rohan Sahariah | Batch 9 | Patharkandi | Karimganj | 5
81 | APU RAY | Tarik Ahmed | Batch 9 | Patharkandi | Karimganj | 9
82 | RUPAM JYOTI GOGOI | Bipul Sonowal | Batch 9 | Dibrugarh East | Dibrugarh | 13
83 | RUPAM JYOTI GOGOI | Bornalee Borah | Batch 9 | Dibrugarh East | Dibrugarh | 8
84 | RUPAM JYOTI GOGOI | Rupi Konwar | Batch 9 | Dibrugarh East | Dibrugarh | 10
85 | RUPAM JYOTI GOGOI | Dimpal Dutta | Batch 9 | Dibrugarh East | Dibrugarh | 15
86 | RUPAM JYOTI GOGOI | Khairul Hussain | Batch 9 | Dibrugarh East | Dibrugarh | 12
87 | RAM DOLEY | Pintu Tanti | Batch 9 | Dibrugarh West | Dibrugarh | 6
88 | RUPAM JYOTI GOGOI | Archana Sonowal | Batch 9 | Dibrugarh East | Dibrugarh | 4
89 | BIPROJIT ROY | Bitu Buragohain | Batch 10 | Badarpur | Karimganj | 7
90 | RUPAM JYOTI GOGOI | Jimbani Dutta | Batch 10/Batch 11 | Dibrugarh East | Dibrugarh | 7
91 | APU RAY | Karishma Ahmed | Batch 10/Batch 11 | Patharkandi | Karimganj | 15
92 | RAM DOLEY | Rajdeep Payang | Batch 10 | Dibrugarh West | Dibrugarh | 15
93 | BIPROJIT ROY | Debajyoti Gogoi | Batch 10 | Badarpur | Karimganj | 7
94 | RAM DOLEY | Rashmi Konwar | Batch 10 | Dibrugarh West | Dibrugarh | 8
95 |  | Abhijit Deori | Batch 10 | Moran | Dibrugarh | 5
96 | RUPAM JYOTI GOGOI | Bikash Rajkhowa | Batch 10 | chabua | Dibrugarh | 4
97 | RUPAM JYOTI GOGOI | Bhaskar Saikia | Batch 10 | chabua | Dibrugarh | 3
98 | RAM DOLEY | Shibani Saikia | Batch 10/Batch 11 | Dibrugarh West | Dibrugarh | 12
99 | RAM DOLEY | Amrit Narah | Batch 10 | Dibrugarh West | Dibrugarh | 5
100 | RUPAM JYOTI GOGOI | Lakhya Taye | Batch 10 | chabua | Dibrugarh | 11
101 | RUPAM JYOTI GOGOI | Joyprasad Taid | Batch 11 | Chabua | Dibrugarh | 10
102 | BIPROJIT ROY | Bidyut Dihingia | Batch 11 | Badarpur | Karimganj | 5
103 | APU RAY | Nurjahan Begum | Batch 12 | Patharkandi | Karimganj | 11
104 | APU RAY | Sopikul Hoque | Batch 12 | Patharkandi | Karimganj | 5
105 | RUPAM JYOTI GOGOI | Arup jyoti Nath | Batch 12 | chabua | Dibrugarh | 10
106 | APU RAY | Tafazul Haque | Batch 12 | Patharkandi | Karimganj | 4
107 | APU RAY | Bhrigu Das | Batch 12 | Patharkandi | Karimganj | 12
108 | RUPAM JYOTI GOGOI | Mokibul Islam | Batch 12 | chabua | Dibrugarh | 15
109 | RUPAM JYOTI GOGOI | Abidul Islam | Batch 12 | chabua | Dibrugarh | 15
110 | BIPROJIT ROY | Aminul Haque Laskar | Batch 12 | Katlichera | Hailakandi | 13
111 | RUPAM JYOTI GOGOI | Arafat Hossain | BATCH 13 | chabua | Dibrugarh | 15
112 | RUPAM JYOTI GOGOI | Bishal Das | BATCH 13 | Chabua | Dibrugarh | 5
113 | APU RAY | Hazrat Ali Rezza | BATCH 13 | Patharkandi | Karimganj | 4
114 | RUPAM JYOTI GOGOI | Hiranya Kumar Gogoi | BATCH 13 | chabua | Dibrugarh | 4
115 |  | Jalaluddin Ahmed | BATCH 13 | moran | Dibrugarh | 9
116 | BIPROJIT ROY | Jiaur Rahman Laskar | BATCH 13 | Hailakandi | Hailakandi | 7
117 |  | Jitu Kalita | BATCH 13 | moran | Dibrugarh | 6
118 | RUPAM JYOTI GOGOI | Joydeep Saikia | BATCH 13 | chabua | Dibrugarh | 7
119 |  | Khaza Faruque Talukdar | BATCH 13 | moran | Dibrugarh | 12
120 |  | Majad Ali | BATCH 13 | moran | Dibrugarh | 7
121 | BIPROJIT ROY | Mirjan Ahmed Laskar | BATCH 13 | Algapur | Hailakandi | 13
122 |  | Priyanka Hazarika | BATCH 13 | moran | Dibrugarh | 13
123 |  | Rahim Badsha | BATCH 13 | moran | Dibrugarh | 12
124 |  | Rakib Uddin | BATCH 13 | moran | Dibrugarh | 12
125 |  | Samidul Islam | BATCH 13 | moran | Dibrugarh | 11
126 |  | Sher Golam Rabbani | BATCH 13 | moran | Dibrugarh | 12
127 | RUPAM JYOTI GOGOI | Shimangshu Baruah | BATCH 13 | Tinsukia | Tinsukia | 4
128 |  | Sirajul Hoque | BATCH 13 | Moran | Dibrugarh | 14
129 | BIPROJIT ROY | Tayabur Rahaman Mazumder | BATCH 13 | Katlichera | Hailakandi | 12
130 | APU RAY | Sumon Kundu | BATCH 13 | RK nagar | Karimganj | 13
131 | APU RAY | Laku Das | BATCH 6 | Patharkandi | Karimganj | 4
132 | RUPAM JYOTI GOGOI | Pranab chutia | Batch 7 | Dibrugarh East | Dibrugarh | 15
133 | APU RAY | Bikash Singha | Batch 14 | Patharkandi | Karimganj | 8
134 | APU RAY | Furkan Ahmed | Batch 14 | Patharkandi | Karimganj | 5
135 | APU RAY | H. Debit Singha | Batch 14 | Patharkandi | Karimganj | 8
136 | APU RAY | Ijaj Ahmed Laskar | Batch 14 | Patharkandi | Karimganj | 12
137 | APU RAY | K. Priyojit Singha | Batch 14 | Patharkandi | Karimganj | 10
138 | APU RAY | Mabrur Ahmed Barbhuiya | Batch 14 | Patharkandi | Karimganj | 13
139 | APU RAY | Probhakar Das | Batch 14 | Patharkandi | Karimganj | 5
140 | APU RAY | Sh Roshan Singha | Batch 14 | Patharkandi | Karimganj | 2
141 | APU RAY | T Nganthoiba Singfha | Batch 14 | Patharkandi | Karimganj | 8
142 | APU RAY | Sirajul Abedin Choudhury | Batch 15 | Patharkandi | Karimganj | 8
143 | APU RAY | Dabit Singha | Batch 14 | Patharkandi | Karimganj | 10
144 | APU RAY | Susmita Rani Das | Batch 15 | Patharkandi | Karimganj | 3
145 | BIPROJIT ROY | Wahiduzzaman Choudhury | Batch 15 | Nilambazar | Karimganj | 14
146 | BIPROJIT ROY | Md. Kamrul Islam | Batch 15 | Nilambazar | Karimganj | 2
147 | BIPROJIT ROY | Shibom Chakraborty | Batch 14 | Nilambazar | Karimganj | 8
148 | BIPROJIT ROY | Shakir Chodhury | Batch 15 | Nilambazar | Karimganj | 11
149 | APU RAY | Suresh Kumar Singha | Batch 14 | Patharkandi | Karimganj | 6
150 | BIPROJIT ROY | Gulzar Hussain | Batch 15 | Nilambazar | Karimganj | 8
151 | BIPROJIT ROY | Nandita Chanda | Batch 15 | Nilambazar | Karimganj | 6
152 | BIPROJIT ROY | Deepshika Dey | Batch 15 | Nilambazar | Karimganj | 3
153 | BIPROJIT ROY | Juber Ahmed | Batch 14 | Nilambazar | Karimganj | 5
154 | BIPROJIT ROY | Drishti Dey | Batch 15 | Nilambazar | Karimganj | 6
155 | BIPROJIT ROY | Mahfuz Hussan | Batch 15 | Nilambazar | Karimganj | 10
156 | APU RAY | Md Jabir Hussain | Batch 14 | RK nagar | Karimganj | 14
157 | APU RAY | Raja Iqbal | Batch 15 | RK nagar | Karimganj | 11
158 | APU RAY | Abdul Ahad | Batch 15 | RK nagar | Karimganj | 10
159 | APU RAY | Satyabrata Deb | Batch 15 | RK nagar | Karimganj | 9
160 | BIPROJIT ROY | Debosree Dhar | Batch 14 | Katlichera | Hailakandi | 10
161 | BIPROJIT ROY | H. Roshan Singha | Batch 14 | Hailakandi | Hailakandi | 11
162 | BIPROJIT ROY | Shramana Singha | Batch 14 | Hailakandi | Hailakandi | 14
163 | BIPROJIT ROY | Abdul Mukit Laskar | Batch 15 | Katlichera | Hailakandi | 14
164 | BIPROJIT ROY | Abu Saleh Ubaidulla Barbhuiya | Batch 15 | Katlichera | Hailakandi | 11
165 | BIPROJIT ROY | Aksor Ahmed Choudhury | Batch 15 | Algapur | Hailakandi | 6
166 | UTPAL RABHA | Kaushik Deka | Batch 15 | Chandrapur | Kamrup M | 10
167 | HUMAYUN KABIR | Sontosh Ali | Batch 3 | BONGAIGAON | BONGAIGAON | 10
168 | HUMAYUN KABIR | Arif Hussain | Batch 3 | BARNAGAR | BARPETA | 10
169 | HUMAYUN KABIR | Saiful Islam | Batch 3 | BARNAGAR | BARPETA | 10
170 |  | Jayanta Hazarika | Batch 3 | GOLAGHAT | GOLAGHAT | 15
171 | TANMOY DUTTA | Nairung Nunisa | Batch 3 | HOJAI | HOJAI | 6
172 | SADULLA HUSSAIN | Abhijit Thakuria | Batch 3 | NALBARI | NALBARI | 10
173 | SADULLA HUSSAIN | Jeherul Islam | Batch 3 | NALBARI | NALBARI | 12
174 | SADULLA HUSSAIN | Pratul Kalita | Batch 3 | NALBARI | NALBARI | 14
175 | SADULLA HUSSAIN | Saidul Hoque | Batch 3 | NALBARI | NALBARI | 15
176 |  | Subhra Jyoti Baruah | Batch 4 | GOLAGHAT | GOLAGHAT | 15
177 | HUMAYUN KABIR | Meherul Islam | Batch 4 | BONGAIGAON | BONGAIGAON | 6
178 | HUMAYUN KABIR | Sibananda Wary | Batch 4 | BONGAIGAON | BONGAIGAON | 10
179 | SADULLA HUSSAIN | Biswajit Kalita | Batch 4 | NALBARI | NALBARI | 14
180 | SADULLA HUSSAIN | Dhrubajyoti Barman | Batch 4 | NALBARI | NALBARI | 10
181 | SADULLA HUSSAIN | Hasimuddin Choudhury | Batch 4 | NALBARI | NALBARI | 12
182 | SADULLA HUSSAIN | Islam Ali | Batch 4 | NALBARI | NALBARI | 10
183 | SADULLA HUSSAIN | Kishor Haloi | Batch 4 | NALBARI | NALBARI | 10
184 | HUMAYUN KABIR | Robiul Hoque | Batch 4 | BARNAGAR | BARPETA | 4
185 | SADULLA HUSSAIN | Jamir Uddin | Batch 5 | NALBARI | NALBARI | 8
186 | SADULLA HUSSAIN | Merajul Ahmed | Batch 5 | NALBARI | NALBARI | 8
187 | SADULLA HUSSAIN | Mostafizur rohman | Batch 5 | NALBARI | NALBARI | 8
188 | SADULLA HUSSAIN | Haidar Ali | Batch 5 | NALBARI | NALBARI | 10
189 | SADULLA HUSSAIN | Ijajul Haque | Batch 5 | NALBARI | NALBARI | 8
190 | SADULLA HUSSAIN | Nurul Islam Choudhury | Batch 5 | NALBARI | NALBARI | 10
191 | TANMOY DUTTA | Md Shaddam Ansari | Batch 5 | HOJAI | HOJAI | 8
192 | KUNAL HAZARIKA | Prantik Deka | Batch 6 | Mangaldoi | DARRANG | 12
193 | KUNAL HAZARIKA | Sanjib Bharali | Batch 6 | Mangaldoi | DARRANG | 10
194 | TANMOY DUTTA | Biswajit Borah | Batch 5 | KAMPUR | NAGAON | 13
195
196
197
198
199
200