## Naksha
Naksha Progress Report
District | Name ULB/Town/ City | Circle | Coordinator Name | Active Surveyors | Daily KPI | 1st-Aug | 2nd-Aug | 4th-Aug | 5th-Aug | 6th-Aug | 7th-Aug | 8th-Aug | 9th-Aug | 11th-Aug | 12th-Aug | 13th-Aug | 14th-Aug | 16th-Aug | 18th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | 27th-Aug | 28th-Aug | 29th-Aug | 30th-Aug | % of 30th-Aug | Total Wards | Running Wards | Total Ward Completed | Pending ward | Completion Date
Bongaigaon | Abhayapuri | Srijangram | Humayun Kabir | 12 | 240 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0; 30th-Aug: 0 |  | 11 | 0 | 11 | 0
Sonitpur | Dhekiajuli MB | Dhekiajuli | Kunal Hazarika | 9 | 180 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0; 30th-Aug: 0 |  | 10 | 0 | 10 | 0
Darrang | Mangaldoi MB | Mangaldoi | Kunal Hazarika | 2 | 40 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0; 30th-Aug: 0 |  | 10 | 0 | 10 | 0
Sivasagar | Sivasagar MB | Sivasagar | Rupam Gogoi | 10 | 200 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0; 30th-Aug: 0 |  | 14 | 0 | 14 | 0
Barpeta | Barpeta Road | Barnagar | Humayun Kabir | 8 | 160 | 53 | 92 | 6 | 72 | 100 | 116 | 110 | 146 | 112 | 23 | 0 | 114 | 53 | 97 | 118 | 124 | 82 | 82 | 20 | 10 | 103 | 98 | 112 | 93 | 84 | 0.525 | 10 | 4 | 6 | 0 | 20th-September | 31st-July
Bongaigaon | Bongaigaon | Bongaigaon | Humayun Kabir | 14 | 280 | 0 | 62 | 0 | 0 | 76 | 111 | 100 | 75 | 36 | 50 | 0 | 169 | 57 | 52 | 71 | 103 | 66 | 27 | 130 | 112 | 76 | 86 | 148 | 46 | 0 | 0 | 25 | 0 | 25 | 0 | 16th-Auguest | 31st-July
Golaghat | Golaghat MB | Golaghat | Dibakar Kalita | 8 | 160 | 0 | 33 | 7 | 63 | 44 | 65 | 31 | 0 | 95 | 118 | 0 | 88 | 0 | 18 | 33 | 63 | 0 | 0 | 0 | 0 | 78 | 113 | 85 | 102 | 97 | 0.60625 | 13 | 6 | 6 | 1 | 12th-October
Hojai | Hojai MB | Hojai | Tonmoy Dutta | 11 | 220 | 0 | 49 | 7 | 112 | 123 | 191 | 197 | 162 | 154 | 130 | 0 | 121 | 48 | 53 | 65 | 90 | 26 | 9 | 90 | 112 | 61 | 14 | 8 | 31 | 21 | 0.095455 | 19 | 1 | 18 | 0 | 15th-September
Nalbari | Nalbari MB | Nalbari | Humayun Kabir | 27 | 540 | 0 | 35 | 0 | 0 | 133 | 227 | 220 | 0 | 213 | 0 | 0 | 0 | 99 | 0 | 64 | 87 | 0 | 0 | 0 | 0 | 204 | 214 | 194 | 210 | 190 | 0.35185 | 17 | 11 | 6 | 0 | 18th-September
Nagaon | Nagaon MB | Nagaon | Tonmoy Dutta | 22 | 440 | 0 | 0 | 0 | 14 | 289 | 324 | 286 | 0 | 242 | 250 | 0 | 337 | 322 | 246 | 135 | 52 | 0 | 0 | 0 | 0 | 249 | 277 | 292 | 298 | 226 | 0.51364 | 26 | 12 | 11 | 3 | 12th-October

## Reservey
Reservey Progress report
Sl No | Survey Areas | Co-ordinator | Circle Name | District Name | Surveyor Deployed | Active Surveyor | Total Villages | Village Completed | Pending Villages | Data Verification | Daily KPI | 1st-Aug | 2nd-Aug | 4th-Aug | 5th-Aug | 6th-Aug | 7th-Aug | 8th-Aug | 9th-Aug | 11th-Aug | 12th-Aug | 13th-Aug | 14th-Aug | 16th-Aug | 18th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | 27th-Aug | 28th-Aug | 29th-Aug | 30th-Aug | % of 30th-Aug | Remarks | Start Date | No of Polygon | Completed Polygon Till Date | End date
1 | NC Forest Reservey | Pradip Saikia | Dhemaji | Dhemaji | 6 | 6 | 8 | 8 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
2 |  | Pradip Saikia | Gogamukh | Dhemaji | 15 | 15 | 18 | 10 | 8 |  | 0 | 164 | 194 | 159 | 241 | 237 | 149 | 77 | 313 | 55 | 338 | 93 | 190 | 253 | 183 | 31 | 16 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
3 |  | Pradip Saikia | Jonai | Dhemaji | 9 | 8 | 22 | 9 | 13 |  | 0 | 87 | 0 | 51 | 0 | 153 | 0 | 98 | 118 | 0 | 87 | 0 | 116 | 8 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
4 |  | Pradip Saikia | Sissiborgaon | Dhemaji | 7 | 0 | 10 | 10 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
5 | Reservey | Ram Kumar Doley | Dibrugarh West | Dibrugarh | 55 | 52 | 169 | 17 | 152 | 5 | 1375 | 0 | 181 | 104 | 320 | 593 | 492 | 463 | 463 | 0 | 328 | 0 | 515 | 397 | 531 | 542 | 214 | 517 | 564 | 583 | 464 | 625 | 561 | 497 | 0 | 0 | 0 | Rain
6 |  | Rupam Jyoti Gogoi | Dibrugarh East | Dibrugarh | 37 | 35 | 116 | 0 | 116 | 10 | 925 | 40 | 48 | 34 | 184 | 333 | 279 | 339 | 346 | 0 | 218 | 4 | 318 | 46 | 314 | 325 | 147 | 272 | 290 | 268 | 263 | 300 | 422 | 410 | 54 | 22 | 0.023784 | Rain
7 |  | Rupam Jyoti Gogoi | Moran | Dibrugarh | 23 | 18 | 60 | 2 | 57 |  | 575 | 66 | 130 | 135 | 173 | 194 | 267 | 223 | 223 | 174 | 114 | 172 | 166 | 0 | 82 | 141 | 161 | 241 | 207 | 210 | 206 | 219 | 208 | 224 | 210 | 0 | 0 | Rain
8 |  | Rupam Jyoti Gogoi | Chabua | Dibrugarh | 27 | 24 | 104 | 2 | 102 | 9 | 675 | 0 | 20 | 26 | 12 | 260 | 335 | 199 | 199 | 0 | 75 | 7 | 153 | 153 | 157 | 146 | 60 | 94 | 107 | 206 | 217 | 206 | 128 | 92 | 67 | 0 | 0 | Rain
10 |  | Rupam Jyoti Gogoi | Tinsukia | Tinsukia | 9 | 7 | 13 | 0 | 13 | 7 | 225 | 0 | 0 | 0 | 33 | 83 | 7 | 120 | 92 | 37 | 36 | 0 | 85 | 150 | 104 | 115 | 27 | 97 | 56 | 35 | 34 | 38 | 40 | 53 | 48 | 33 | 0.14667 | Rain
11 |  | Biprojit Roy | Algapur | Hailakandi | 7 | 7 | 11 | 1 | 10 | 1 | 175 | 54 | 28 | 2 | 25 | 66 | 61 | 60 | 68 | 59 | 69 | 7 | 82 | 76 | 62 | 63 | 75 | 34 | 58 | 98 | 83 | 81 | 71 | 52 | 67 | 87 | 0.49714 |  | 10th-May | 5100 | 3782
12 |  | Biprojit Roy | Hailakandi | Hailakandi | 7 | 6 | 7 | 1 | 6 | 1 | 175 | 53 | 55 | 0 | 37 | 33 | 43 | 47 | 55 | 76 | 65 | 15 | 59 | 60 | 29 | 58 | 63 | 13 | 26 | 66 | 64 | 75 | 62 | 81 | 73 | 80 | 0.45714 |  | 20th-May | 2955
13 |  | Biprojit Roy | Lala | Hailakandi | 1 | 0 | 2 | 0 | 2 |  | 25 | 21 | 17 | 0 | 4 | 0 | 8 | 2 | 3 | 5 | 4 | 0 | 4 | 5 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 4 | 3 | 3 | 0 | 0
14 |  | Biprojit Roy | Katlichera | Hailakandi | 7 | 7 | 7 | 0 | 7 | 1 | 175 | 60 | 72 | 0 | 75 | 78 | 96 | 104 | 91 | 105 | 78 | 70 | 97 | 105 | 114 | 92 | 69 | 26 | 59 | 81 | 75 | 88 | 86 | 83 | 77 | 76 | 0.43429 |  | 15th-May | 4080
15 |  | Biprojit Roy | Badarpur | Shribhumi | 25 | 25 | 61 | 0 | 61 | 2 | 625 | 170 | 159 | 36 | 179 | 290 | 319 | 273 | 287 | 290 | 337 | 83 | 315 | 197 | 212 | 210 | 237 | 145 | 199 | 244 | 292 | 272 | 241 | 201 | 309 | 322 | 0.5152 |  | 15th-May | 28470
16 |  | Biprojit Roy | Shribhumi Sadar | Shribhumi | 10 | 8 | 45 | 1 | 44 | 1 | 250 | 14 | 30 | 9 | 10 | 62 | 46 | 63 | 79 | 58 | 34 | 35 | 70 | 44 | 45 | 59 | 46 | 24 | 19 | 23 | 58 | 73 | 62 | 18 | 69 | 92 | 0.368 |  | 10th-May | 3630
17 |  | Biprojit Roy | Nilambazar | Shribhumi | 20 | 19 | 65 | 0 | 65 | 3 | 500 | 158 | 148 | 88 | 52 | 41 | 170 | 55 | 108 | 107 | 154 | 88 | 145 | 157 | 110 | 147 | 124 | 22 | 43 | 148 | 95 | 124 | 125 | 90 | 67 | 122 | 0.244 |  | 10th-May | 5716
18 |  | Apu Ray | Rk Nagar | Shribhumi | 31 | 28 | 96 | 8 | 88 | 0 | 775 | 95 | 141 | 58 | 164 | 103 | 132 | 125 | 161 | 183 | 181 | 207 | 168 | 188 | 220 | 165 | 217 | 74 | 131 | 216 | 196 | 170 | 209 | 204 | 161 | 181 | 0.23355 |  | 15th-May | 13287 | 9683
19 |  | Apu Ray | Patharkandi | Shribhumi | 54 | 48 | 151 | 0 | 151 | 2 | 1350 | 262 | 273 | 36 | 198 | 32 | 152 | 292 | 312 | 365 | 362 | 62 | 396 | 323 | 299 | 310 | 346 | 10 | 133 | 334 | 316 | 314 | 305 | 313 | 279 | 423 | 0.31333 |  | 15th-May | 21433 | 12219
20 |  | Utpal Rabha | Chandrapur | Kamrup M | 24 | 24 | 37 | 4 | 33 | 9 | 600 | 143 | 0 | 43 | 18 | 235 | 305 | 269 | 242 | 308 | 179 | 7 | 44 | 28 | 74 | 181 | 227 | 12 | 38 | 304 | 290 | 281 | 220 | 183 | 251 | 214 | 0.35667 |  | 10th-May | 20799 | 11600
21 |  | Humayun Kabir | Agomani | Dhubri | 7 | 4 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 55 | 41 | 42 | 44 | 46 | 36 | 33 | 13 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
22 | NC | Humayun Kabir | Baghbar | Barpeta | 3 | 3 | 3 | 0 | 3 | 3 | 75 | 112 | 132 | 10 | 25 | 82 | 58 | 46 | 83 | 53 | 55 | 31 | 95 | 71 | 45 | 55 | 91 | 57 | 89 | 100 | 74 | 97 | 73 | 89 | 76 | 117 | 1.56
23 |  | Tanmoy Dutta | Kampur | Nagaon | 5 | 5 | 6 | 1 | 5 |  | 125 | 93 | 91 | 84 | 118 | 126 | 98 | 133 | 125 | 136 | 128 | 0 | 73 | 123 | 111 | 116 | 124 | 104 | 64 | 60 | 46 | 60 | 33 | 31 | 123 | 88 | 0.704
|  |  | Total | [7 empty] | 8625 | 1592 | 1719 | 875 | 1923 | 3042 | 3059 | 3032 | 3414 | 2047 | 2875 | 894 | 3091 | 2384 | 2861 | 2764 | 2244 | 1776 | 2083 | 2984 | 2781 | 3031 | 2850 | 2624 | 1934 | 1857 | 0.2153

## FC_Performance Matrix-July-25
1st - 30th Aug Coordinator Progress Report
Co-ordinator Name | Survey Areas | District Name | Surveyor Deployed | Active Surveyor | Dag per Surveyor | Target Dag | 2025-08-01 | 2025-08-02 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-11 | 2025-08-12 | 13th-Aug | 14th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | % of 26th-Aug Achieved Dags | 27th-Aug | 28th-Aug | 29th-Aug | 30th-Aug | % of 30th-Aug Achieved Dags
Dibakar Kalita | Reservey/Naksha | Golaghat | 29 | 20 | 20&25 | 160 | 66 | 163 | 142 | 236 | 238 | 332 | 254 | 223 | 269 | 232 | 172 | 254 | 194 | 224 | 241 | 207 | 210 | 0 | 78 | 0.4875 | 113 | 85 | 102 | 97 | 0.60625
Tanmoy Dutta | Naksha/NC | Nagaon/Hojai | 36 | 35 | 20&25 | 770 | 93 | 140 | 91 | 244 | 537 | 613 | 616 | 287 | 532 | 508 | 0 | 531 | 316 | 266 | 130 | 73 | 150 | 158 | 370 | 0.48052 | 324 | 331 | 452 | 335 | 0.43506
Biprojit Roy | Reservey | Shribhumi/Hailakandi | 78 | 68 | 25 | 1925 | 530 | 509 | 135 | 382 | 570 | 743 | 604 | 691 | 700 | 741 | 298 | 772 | 637 | 617 | 242 | 404 | 668 | 675 | 721 | 0.37455 | 651 | 528 | 665 | 779 | 0.40468
Utpal Rabha | Reservey | Kamrup M | 24 | 22 | 25 | 720 | 143 | 0 | 43 | 18 | 235 | 305 | 269 | 242 | 308 | 179 | 7 | 44 | 181 | 227 | 12 | 38 | 304 | 290 | 281 | 0.39028 | 220 | 183 | 251 | 214 | 0.29722
Apu Ray | Reservey | Shribhumi | 85 | 81 | 25 | 2125 | 357 | 414 | 94 | 362 | 135 | 284 | 417 | 473 | 548 | 543 | 269 | 564 | 475 | 563 | 84 | 264 | 550 | 512 | 484 | 0.22776 | 514 | 517 | 440 | 604 | 0.28424
Humayun Kabir | Reservey/Naksha/NC | Bongaigaon/Nalbari/Barpeta/Dhubri | 69 | 61 | 20&25 | 1415 | 167 | 321 | 16 | 152 | 432 | 554 | 520 | 350 | 450 | 161 | 44 | 378 | 308 | 405 | 205 | 198 | 250 | 196 | 480 | 0.33922 | 471 | 543 | 425 | 391 | 0.27633
Rupam Jyoti Gogoi | Reservey/Naksha | Dibrugarh/Tinsukia/Sivsagar | 76 | 76 | 25 | 2400 | 40 | 68 | 34 | 229 | 676 | 621 | 658 | 637 | 37 | 218 | 11 | 556 | 586 | 234 | 463 | 453 | 509 | 720 | 763 | 0.31792 | 758 | 779 | 379 | 55 | 0.022917
Ram Kumar Doley | Reservey | Dibrugarh | 55 | 46 | 25 | 1375 | 0 | 181 | 104 | 320 | 593 | 492 | 463 | 463 | 0 | 328 | 0 | 515 | 542 | 214 | 517 | 564 | 583 | 464 | 625 | 0.45455 | 561 | 497 | 0 | 0 | 0
Pradip Saikia | NC Forest Reservey | Dhemaji | 29 | 26 | 25 | 0 | 251 | 194 | 210 | 241 | 390 | 149 | 175 | 431 | 55 | 425 | 93 | 306 | 31 | 16 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project-Overview
Present Status |  | Work in Progress
Item | Details | Activity | Status
Survey Completed (NC Villages) | 531 villages | Re-Survey Operations | Ongoing in 926 villages across 6 districts
Survey Completed (NC Forest Villages) | 64 villages
Total Property Details (NAKSHA) | 251067 | NC Survey Operations | Ongoing in 6 villages
Properties Surveyed (NAKSHA Project) | 88704 | NAKSHA Survey Operations | Active in 35 wards
Pending Property Details | 162363
ULBs Covered Under NAKSHA | 10 ULBs (Total Wards: 155)
Wards Completed Under NAKSHA | 117 Wards
Property Completion-Naksha |  | Reservey Villages Details | Count
Properties Completed - Nagaon | 17109 (51074) | Total Villages (Resurvey) | 926
Properties Completed - Hojai | 5652 (16741) | Villages Completed(Reservey) | 36
Properties Completed - Barpeta Road | 9098 (19767) | Villages in Data Verification Process | 58
Properties Completed - Bongaigaon | 12748 (41125) | Ongoing Villages | 287
Properties Completed - Abhayapuri | 5816 (7987)
Properties Completed - Nalbari | 9202 (35835)
Properties Completed - Mangaldoi | 4559 (21648) | Field Coordinator | Active Villages | Below 50% Completion | Above 50% Completion | Above 80% Completion | Almost Completed
Properties Completed - Dhekiajuli | 8976 (16725) | Apu Ray | 59 | 29 | 18 | 5 | 7
Properties Completed - Sivasagar | 10343 (19485) | Biprojit Roy | 72 | 0 | 53 | 12 | 7
Properties Completed - Golaghat | 5072 (20678) | Rupam Gogoi | 69 | 29 | 33 | 7 | 0
Re-Survey Villages Completed |  | Raam Doley | 51 | 21 | 22 | 0 | 8
Re-Survey Villages Completed | 37 villages | Utpal Rabha | 14 | 11 | 3 | 0 | 5
Re-Survey Circles Covered | Dibrugarh West, Chandrapur, Chabua,Kampur,Moran,algapur,sadar,algapur,Hailakandi | Pradip Saikia | 0 | 0 | 0 | 0 | 0
HRs Details |  | Dibakar Kalita | 19 | 8 | 11
Active Teams | 551
HRs in Survey/Re-Survey | 384
HRs in NC Survey | 6
HRs in NAKSHA | 161
Additional HRs Ready to Deploy | 49
Assistant Surveyors at Worksites | 551
Re-Survey Work Issues |  | NAKSHA Project Issues
Problem Area | Description | Problem Area | Description
Network Connectivity | Non-availability in remote areas | Municipality Coordination | Lack of presence of Municipality Member/Text Collector delays verification
HR Challenges | Public reluctance, lack of cooperation | Multiple Site Visits | Owners unaware of survey schedule, leading to repeated site visits
Device Problems | CORS ID auth issues, Trimble malfunctions | Surveyor Access Restrictions | Owners allow survey only when accompanied by a Municipality Member
Vehicle Issues | Breakdowns and transport unavailability | Data Synchronization | Network issues causing delays
Weather Challenges | Heavy rain, extreme heat hampering field work | Property Owner Availability | Unavailable during visits, slowing verification
|  | Public Awareness | Lack of understanding causing resistance/misinformation
|  | Weather & Logistics | Rains, heat, transport issues

## Less than 16 Dags
SURVEYOR COLLECTED LESS THEN 15 DAG ON 30th-Aug
Sl No | Field Coordinator | Name of the Hired Surveyor | Batch No | Circle Name | District Name | Dag
1 | BIPROJIT ROY | Koyes Ahmed Barbuiya | Batch 3 | Algapur | Hailakandi | 8
2 | BIPROJIT ROY | Pradip Riang | Batch 3 | Algapur | Hailakandi | 14 | Today present 470
3 | APU RAY | Rohit Kumar Paul | Batch 3 | RK nagar | Karimganj | 7 | 0 dag - 282
4 | APU RAY | Amir Das | Batch 3 | RK nagar | Karimganj | 5 | 1 to 5 - 23
5 | UTPAL RABHA | Suju Kr Gayari | Batch 3 | Chandrapur | Kamrup M | 1 | 6 to 15 - 112
6 | APU RAY | Reemi Barman | Batch 4 | RK nagar | Karimganj | 10 | 16 or greater - 53
7 | BIPROJIT ROY | Biktur Das | Batch 4 | Algapur | Hailakandi | 5
8 | APU RAY | Arup Goswami | Batch 4 | Patharkandi | Karimganj | 12 | Total rover used - 145
9 | BIPROJIT ROY | Annu Arddao | Batch 4 | Shribhumi Sadar | Karimganj | 12 | Total points collected - 8717
10 | APU RAY | Jyotisman Deka | Batch 4 | Patharkandi | Karimganj | 10 | Total surveyor present - 341
11 | APU RAY | Rezanuj Zaman | Batch 5 | Patharkandi | Karimganj | 10 | Surveyors collected more than 50 points - 81
12 | BIPROJIT ROY | Josmaidao Thaosen | Batch 5 | Shribhumi Sadar | Karimganj | 13 | % of Surveyors collect more than 50 points today - 23.75
13 | BIPROJIT ROY | Lasmi Debragede | Batch 5 | Shribhumi Sadar | Karimganj | 5
14 | BIPROJIT ROY | Rahul Langthasa | Batch 5 | Shribhumi Sadar | Karimganj | 11
15 | APU RAY | Sohamdao Naiding | Batch 5 | Patharkandi | Karimganj | 5
16 | BIPROJIT ROY | Sunabi Johori | Batch 5 | Shribhumi Sadar | Karimganj | 7
17 | APU RAY | Kamal Rajbongshi | Batch 5 | Patharkandi | Karimganj | 8
18 | APU RAY | Sanjoy Shyam | Batch 5 | Patharkandi | Karimganj | 10
19 | UTPAL RABHA | Abdul Sarwer Mintu | Batch 6 | Chandrapur | Kamrup M | 10
20 | UTPAL RABHA | Mozahar Rahman | Batch 6 | Chandrapur | Kamrup M | 10
21 | UTPAL RABHA | Prasenjit Barman | Batch 6 | Chandrapur | Kamrup M | 11
22 | UTPAL RABHA | Jillur Rahman | Batch 6 | Chandrapur | Kamrup M | 11
23 | BIPROJIT ROY | Nur Alom Sheikh | Batch 6 | Badarpur | Karimganj | 4
24 | BIPROJIT ROY | Altaf Hussain Barbhuiyan | Batch 6 | Katlichera | Hailakandi | 9
25 | APU RAY | Azmal Hussain Choudhury | Batch 6 | RK nagar | Karimganj | 13
26 | APU RAY | Dhrubojyoti Roy | Batch 6 | RK nagar | Karimganj | 10
27 | APU RAY | Sujata Das | Batch 6 | RK nagar | Karimganj | 4
28 | UTPAL RABHA | Rituparna Saikia | Batch 6 | Chandrapur | Kamrup M | 12
29 | BIPROJIT ROY | Ashan Ali | Batch 6 | Badarpur | Karimganj | 12
30 | BIPROJIT ROY | Hasen Ali | Batch 6 | Badarpur | Karimganj | 7
31 | APU RAY | Imran Hussain | Batch 6 | Patharkandi | Karimganj | 2
32 | APU RAY | Eunus Ali | Batch 6 | Patharkandi | Karimganj | 5
33 | APU RAY | Rajdeep Das | Batch 7 | RK nagar | Karimganj | 2
34 | APU RAY | Sukanta Das | Batch 8 | RK nagar | Karimganj | 5
35 | BIPROJIT ROY | Mridul Boruah | Batch 8 | Badarpur | Karimganj | 11
36 | BIPROJIT ROY | Nabajyoti Kalita | Batch 8 | Badarpur | Karimganj | 14
37 | BIPROJIT ROY | Abul Hussain | Batch 8 | Badarpur | Karimganj | 10
38 | UTPAL RABHA | Swapnali Baruah | Batch 8 | Chandrapur | Kamrup M | 14
39 | RUPAM JYOTI GOGOI | Bhaben Chutia | Batch 8 | Dibrugarh East | Dibrugarh | 5
40 | RUPAM JYOTI GOGOI | Mridupaban Gogoi | Batch 8 | Dibrugarh East | Dibrugarh | 8
41 | RUPAM JYOTI GOGOI | Dibyajyoti Boruah | Batch 8 | Dibrugarh East | Dibrugarh | 9
42 | APU RAY | Gunindra Deuri | Batch 8 | Patharkandi | Karimganj | 9
43 | APU RAY | Lila Prosad Deuri | Batch 8 | Patharkandi | Karimganj | 11
44 | APU RAY | Amar Jyoti Baruah | Batch 9 | Patharkandi | Karimganj | 6
45 | BIPROJIT ROY | Ataur Rahman | Batch 9 | Badarpur | Karimganj | 8
46 | BIPROJIT ROY | Hemanta Boro | Batch 9 | Badarpur | Karimganj | 7
47 | APU RAY | Rohan Sahariah | Batch 9 | Patharkandi | Karimganj | 2
48 | APU RAY | Tarik Ahmed | Batch 9 | Patharkandi | Karimganj | 9
49 | BIPROJIT ROY | Debajyoti Gogoi | Batch 10 | Badarpur | Karimganj | 10
50 | APU RAY | Sulaiman Ali | Batch 10 | Patharkandi | Karimganj | 10
51 | RUPAM JYOTI GOGOI | Poonam Barman | Batch 11 | Tinsukia | Tinsukia | 1
52 | BIPROJIT ROY | Bidyut Dihingia | Batch 11 | Badarpur | Karimganj | 12
53 | APU RAY | Nurjahan Begum | Batch 12 | Patharkandi | Karimganj | 7
54 | APU RAY | Sopikul Hoque | Batch 12 | Patharkandi | Karimganj | 7
55 | BIPROJIT ROY | Abdul Wahab | Batch 12 | Badarpur | Karimganj | 11
56 | APU RAY | Gofiur Rahman | Batch 12 | Patharkandi | Karimganj | 12
57 | APU RAY | Tafazul Haque | Batch 12 | Patharkandi | Karimganj | 6
58 | APU RAY | Bhrigu Das | Batch 12 | Patharkandi | Karimganj | 13
59 | BIPROJIT ROY | Mohir Uddin | Batch 12 | Badarpur | Karimganj | 13
60 | APU RAY | Hazrat Ali Rezza | BATCH 13 | Patharkandi | Karimganj | 6
61 | BIPROJIT ROY | Jiaur Rahman Laskar | BATCH 13 | Hailakandi | Hailakandi | 12
62 | RUPAM JYOTI GOGOI | Shimangshu Baruah | BATCH 13 | Tinsukia | Tinsukia | 5
63 | BIPROJIT ROY | Tayabur Rahaman Mazumder | BATCH 13 | Katlichera | Hailakandi | 10
64 | APU RAY | Sumon Kundu | BATCH 13 | RK nagar | Karimganj | 13
65 | APU RAY | Laku Das | BATCH 6 | Patharkandi | Karimganj | 2
66 | RUPAM JYOTI GOGOI | Jitul doley | Batch 7 | tinsukia | TINSUKIA | 11
67 | RUPAM JYOTI GOGOI | Manjil Payeng | Batch 9 | tinsukia | TINSUKIA | 6
68 | RUPAM JYOTI GOGOI | Anamika buragohain | Batch 5 | tinsukia | TINSUKIA | 4
69 | RUPAM JYOTI GOGOI | NISHIGANDHA GOGOI | Batch 12 | tinsukia | TINSUKIA | 6
70 | APU RAY | Bikash Singha | Batch 14 | Patharkandi | Karimganj | 9
71 | APU RAY | Furkan Ahmed | Batch 14 | Patharkandi | Karimganj | 10
72 | APU RAY | H. Debit Singha | Batch 14 | Patharkandi | Karimganj | 9
73 | APU RAY | Ijaj Ahmed Laskar | Batch 14 | Patharkandi | Karimganj | 11
74 | APU RAY | K. Priyojit Singha | Batch 14 | Patharkandi | Karimganj | 10
75 | APU RAY | Mabrur Ahmed Barbhuiya | Batch 14 | Patharkandi | Karimganj | 12
76 | APU RAY | Probhakar Das | Batch 14 | Patharkandi | Karimganj | 7
77 | APU RAY | Santosh Kumar Kanu | Batch 14 | Patharkandi | Karimganj | 10
78 | APU RAY | Sh Roshan Singha | Batch 14 | Patharkandi | Karimganj | 7
79 | APU RAY | T Nganthoiba Singfha | Batch 14 | Patharkandi | Karimganj | 11
80 | APU RAY | Tinki Nag | Batch 14 | Patharkandi | Karimganj | 10
81 | APU RAY | Sirajul Abedin Choudhury | Batch 15 | Patharkandi | Karimganj | 5
82 | APU RAY | Debangli Das | Batch 14 | Patharkandi | Karimganj | 10
83 | APU RAY | Dabit Singha | Batch 14 | Patharkandi | Karimganj | 7
84 | APU RAY | Susmita Rani Das | Batch 15 | Patharkandi | Karimganj | 6
85 | APU RAY | L. Bikram Singha | Batch 14 | Patharkandi | Karimganj | 3
86 | BIPROJIT ROY | Sultan Ahmed | Batch 14 | Nilambazar | Karimganj | 10
87 | APU RAY | Suresh Kumar Singha | Batch 14 | Patharkandi | Karimganj | 6
88 | BIPROJIT ROY | Gulzar Hussain | Batch 15 | Nilambazar | Karimganj | 11
89 | BIPROJIT ROY | Juber Ahmed | Batch 14 | Nilambazar | Karimganj | 5
90 | BIPROJIT ROY | Drishti Dey | Batch 15 | Nilambazar | Karimganj | 8
91 | BIPROJIT ROY | Mahfuz Hussan | Batch 15 | Nilambazar | Karimganj | 12
92 | APU RAY | Md Jabir Hussain | Batch 14 | RK nagar | Karimganj | 7
93 | APU RAY | Abdul Ahad | Batch 15 | RK nagar | Karimganj | 10
94 | APU RAY | Satyabrata Deb | Batch 15 | RK nagar | Karimganj | 6
95 | BIPROJIT ROY | Prabal Chakraborty | Batch 15 | Nilambazar | Karimganj | 10
96 | BIPROJIT ROY | Debosree Dhar | Batch 14 | Katlichera | Hailakandi | 6
97 | BIPROJIT ROY | Abdul Mukit Laskar | Batch 15 | Katlichera | Hailakandi | 10
98 | BIPROJIT ROY | Abu Saleh Ubaidulla Barbhuiya | Batch 15 | Katlichera | Hailakandi | 8
99 | BIPROJIT ROY | Aksor Ahmed Choudhury | Batch 15 | Algapur | Hailakandi | 13
100 | UTPAL RABHA | Biki Boro | Batch 15 | Chandrapur | Kamrup M | 9
101 | TANMOY DUTTA | Biswajit Ghosh | Batch 1 | NAGAON | NAGAON | 12
102 | TANMOY DUTTA | Deep Sonowal | Batch 1 | NAGAON | NAGAON | 14
103 | TANMOY DUTTA | Khagen Gogoi | Batch 2 | NAGAON | NAGAON | 14
104 | HUMAYUN KABIR | Arif Hussain | Batch 3 | BARNAGAR | BARPETA | 12
105 | HUMAYUN KABIR | Saiful Islam | Batch 3 | BARNAGAR | BARPETA | 10
106 | SADULLA HUSSAIN | Abhijit Thakuria | Batch 3 | NALBARI | NALBARI | 10
107 | SADULLA HUSSAIN | Jeherul Islam | Batch 3 | NALBARI | NALBARI | 10
108 | SADULLA HUSSAIN | Mohijul Hoque | Batch 3 | NALBARI | NALBARI | 13
109 | SADULLA HUSSAIN | Niran Kathar | Batch 3 | NALBARI | NALBARI | 14
110 | SADULLA HUSSAIN | Saidul Hoque | Batch 3 | NALBARI | NALBARI | 13
111 | SADULLA HUSSAIN | Biswajit Kalita | Batch 4 | NALBARI | NALBARI | 14
112 | SADULLA HUSSAIN | Dhrubajyoti Barman | Batch 4 | NALBARI | NALBARI | 10
113 | SADULLA HUSSAIN | Hasimuddin Choudhury | Batch 4 | NALBARI | NALBARI | 10
114 | SADULLA HUSSAIN | Islam Ali | Batch 4 | NALBARI | NALBARI | 11
115 | TANMOY DUTTA | Eusuf Ali | Batch 4 | HOJAI | HOJAI | 11
116 | SADULLA HUSSAIN | Mostafizur rohman | Batch 5 | NALBARI | NALBARI | 12
117 | SADULLA HUSSAIN | Haidar Ali | Batch 5 | NALBARI | NALBARI | 11
118 | SADULLA HUSSAIN | Ijajul Haque | Batch 5 | NALBARI | NALBARI | 5
119 | SADULLA HUSSAIN | Nurul Islam Choudhury | Batch 5 | NALBARI | NALBARI | 5
120 | TANMOY DUTTA | Ibrahim Ali | Batch 5 | HOJAI | HOJAI | 10
121 | KUNAL HAZARIKA | Sanjib Bharali | Batch 6 | Mangaldoi | DARRANG | 2
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200