## Naksha
Naksha Progress Report
District | Name ULB/Town/ City | Circle | Coordinator Name | Active Surveyors | Daily KPI | 1st-Aug | 2nd-Aug | 4th-Aug | 5th-Aug | 6th-Aug | 7th-Aug | 8th-Aug | 9th-Aug | 11th-Aug | 12th-Aug | 13th-Aug | 14th-Aug | 16th-Aug | 18th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | 27th-Aug | 28th-Aug | % of 28th-Aug | Total Wards | Running Wards | Total Ward Completed | Pending ward | Completion Date
Bongaigaon | Abhayapuri | Srijangram | Humayun Kabir | 12 | 240 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0 |  | 11 | 0 | 11 | 0
Sonitpur | Dhekiajuli MB | Dhekiajuli | Kunal Hazarika | 9 | 180 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0 |  | 10 | 0 | 10 | 0
Darrang | Mangaldoi MB | Mangaldoi | Kunal Hazarika | 2 | 40 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0 |  | 10 | 0 | 10 | 0
Sivasagar | Sivasagar MB | Sivasagar | Rupam Gogoi | 10 | 200 | 1st-Aug: 0; 2nd-Aug: 0; 4th-Aug: 0; 5th-Aug: 0; 6th-Aug: 0; 7th-Aug: 0; 8th-Aug: 0; 9th-Aug: 0; 11th-Aug: 0; 12th-Aug: 0; 13th-Aug: 0; 14th-Aug: 0; 22nd-Aug: 0 |  | 14 | 0 | 14 | 0
Barpeta | Barpeta Road | Barnagar | Humayun Kabir | 8 | 160 | 53 | 92 | 6 | 72 | 100 | 116 | 110 | 146 | 112 | 23 | 0 | 114 | 53 | 97 | 118 | 124 | 82 | 82 | 20 | 10 | 103 | 98 | 112 | 0.7 | 10 | 4 | 6 | 0 | 20th-Auguest | 31st-July
Bongaigaon | Bongaigaon | Bongaigaon | Humayun Kabir | 14 | 280 | 0 | 62 | 0 | 0 | 76 | 111 | 100 | 75 | 36 | 50 | 0 | 169 | 57 | 52 | 71 | 103 | 66 | 27 | 130 | 112 | 76 | 86 | 148 | 0.52857 | 25 | 1 | 24 | 0 | 16th-Auguest | 31st-July
Golaghat | Golaghat MB | Golaghat | Dibakar Kalita | 8 | 160 | 0 | 33 | 7 | 63 | 44 | 65 | 31 | 0 | 95 | 118 | 0 | 88 | 0 | 18 | 33 | 63 | 0 | 0 | 0 | 0 | 78 | 113 | 85 | 0.53125 | 13 | 6 | 6 | 1 | 30th-October
Hojai | Hojai MB | Hojai | Tonmoy Dutta | 11 | 220 | 0 | 49 | 7 | 112 | 123 | 191 | 197 | 162 | 154 | 130 | 0 | 121 | 48 | 53 | 65 | 90 | 26 | 9 | 90 | 112 | 61 | 14 | 8 | 0.036364 | 19 | 1 | 18 | 0 | 15th-September
Nalbari | Nalbari MB | Nalbari | Humayun Kabir | 27 | 540 | 0 | 35 | 0 | 0 | 133 | 227 | 220 | 0 | 213 | 0 | 0 | 0 | 99 | 0 | 64 | 87 | 0 | 0 | 0 | 0 | 204 | 214 | 194 | 0.35926 | 17 | 11 | 6 | 0 | 18th-September
Nagaon | Nagaon MB | Nagaon | Tonmoy Dutta | 22 | 440 | 0 | 0 | 0 | 14 | 289 | 324 | 286 | 0 | 242 | 250 | 0 | 337 | 322 | 246 | 135 | 52 | 0 | 0 | 0 | 0 | 249 | 277 | 292 | 0.66364 | 26 | 12 | 11 | 3 | 12th-October

## Reservey
Reservey Progress report
Sl No | Survey Areas | Co-ordinator | Circle Name | District Name | Surveyor Deployed | Active Surveyor | Total Villages | Village Completed | Pending Villages | Data Verification | Daily KPI | 1st-Aug | 2nd-Aug | 4th-Aug | 5th-Aug | 6th-Aug | 7th-Aug | 8th-Aug | 9th-Aug | 11th-Aug | 12th-Aug | 13th-Aug | 14th-Aug | 16th-Aug | 18th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | 27th-Aug | 28th-Aug | % of 28th-Aug | Remarks | Start Date | No of Polygon | Completed Polygon Till Date | End date
1 | NC Forest Reservey | Pradip Saikia | Dhemaji | Dhemaji | 6 | 0 | 8 | 8 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
2 |  | Pradip Saikia | Gogamukh | Dhemaji | 15 | 15 | 18 | 10 | 8 |  | 0 | 164 | 194 | 159 | 241 | 237 | 149 | 77 | 313 | 55 | 338 | 93 | 190 | 253 | 183 | 31 | 16 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
3 |  | Pradip Saikia | Jonai | Dhemaji | 9 | 7 | 22 | 9 | 13 |  | 0 | 87 | 0 | 51 | 0 | 153 | 0 | 98 | 118 | 0 | 87 | 0 | 116 | 8 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
4 |  | Pradip Saikia | Sissiborgaon | Dhemaji | 7 | 7 | 10 | 10 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Village Completed
5 | Reservey | Ram Kumar Doley | Dibrugarh West | Dibrugarh | 55 | 52 | 169 | 17 | 152 | 5 | 1375 | 0 | 181 | 104 | 320 | 593 | 492 | 463 | 463 | 0 | 328 | 0 | 515 | 397 | 531 | 542 | 214 | 517 | 564 | 583 | 464 | 625 | 561 | 497 | 0.36145
6 |  | Rupam Jyoti Gogoi | Dibrugarh East | Dibrugarh | 37 | 31 | 116 | 0 | 116 | 9 | 925 | 40 | 48 | 34 | 184 | 333 | 279 | 339 | 346 | 0 | 218 | 4 | 318 | 46 | 314 | 325 | 147 | 272 | 290 | 268 | 263 | 300 | 422 | 410 | 0.44324
7 |  | Rupam Jyoti Gogoi | Moran | Dibrugarh | 23 | 18 | 60 | 2 | 57 |  | 575 | 66 | 130 | 135 | 173 | 194 | 267 | 223 | 223 | 174 | 114 | 172 | 166 | 0 | 82 | 141 | 161 | 241 | 207 | 210 | 206 | 219 | 208 | 224 | 0.38957
8 |  | Rupam Jyoti Gogoi | Chabua | Dibrugarh | 27 | 23 | 104 | 2 | 102 | 7 | 675 | 0 | 20 | 26 | 12 | 260 | 335 | 199 | 199 | 0 | 75 | 7 | 153 | 153 | 157 | 146 | 60 | 94 | 107 | 206 | 217 | 206 | 128 | 92 | 0.1363
10 |  | Rupam Jyoti Gogoi | Tinsukia | Tinsukia | 9 | 7 | 13 | 0 | 13 | 7 | 225 | 0 | 0 | 0 | 33 | 83 | 7 | 120 | 92 | 37 | 36 | 0 | 85 | 150 | 104 | 115 | 27 | 97 | 56 | 35 | 34 | 38 | 40 | 53 | 0.23556
11 |  | Biprojit Roy | Algapur | Hailakandi | 7 | 7 | 11 | 1 | 10 | 1 | 175 | 54 | 28 | 2 | 25 | 66 | 61 | 60 | 68 | 59 | 69 | 7 | 82 | 76 | 62 | 63 | 75 | 34 | 58 | 98 | 83 | 81 | 71 | 52 | 0.29714 |  | 10th-May | 5100 | 3782
12 |  | Biprojit Roy | Hailakandi | Hailakandi | 7 | 5 | 7 | 1 | 6 | 1 | 175 | 53 | 55 | 0 | 37 | 33 | 43 | 47 | 55 | 76 | 65 | 15 | 59 | 60 | 29 | 58 | 63 | 13 | 26 | 66 | 64 | 75 | 62 | 81 | 0.46286 |  | 20th-May | 2955
13 |  | Biprojit Roy | Lala | Hailakandi | 1 | 1 | 2 | 0 | 2 |  | 25 | 21 | 17 | 0 | 4 | 0 | 8 | 2 | 3 | 5 | 4 | 0 | 4 | 5 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 4 | 3 | 0.12
14 |  | Biprojit Roy | Katlichera | Hailakandi | 7 | 7 | 7 | 0 | 7 | 1 | 175 | 60 | 72 | 0 | 75 | 78 | 96 | 104 | 91 | 105 | 78 | 70 | 97 | 105 | 114 | 92 | 69 | 26 | 59 | 81 | 75 | 88 | 86 | 83 | 0.47429 |  | 15th-May | 4080
15 |  | Biprojit Roy | Badarpur | Shribhumi | 25 | 21 | 61 | 0 | 61 | 2 | 625 | 170 | 159 | 36 | 179 | 290 | 319 | 273 | 287 | 290 | 337 | 83 | 315 | 197 | 212 | 210 | 237 | 145 | 199 | 244 | 292 | 272 | 241 | 201 | 0.3216 |  | 15th-May | 28470
16 |  | Biprojit Roy | Shribhumi Sadar | Shribhumi | 10 | 8 | 45 | 1 | 44 | 1 | 250 | 14 | 30 | 9 | 10 | 62 | 46 | 63 | 79 | 58 | 34 | 35 | 70 | 44 | 45 | 59 | 46 | 24 | 19 | 23 | 58 | 73 | 62 | 18 | 0.072 |  | 10th-May | 3630
17 |  | Biprojit Roy | Nilambazar | Shribhumi | 20 | 19 | 65 | 0 | 65 | 3 | 500 | 158 | 148 | 88 | 52 | 41 | 170 | 55 | 108 | 107 | 154 | 88 | 145 | 157 | 110 | 147 | 124 | 22 | 43 | 148 | 95 | 124 | 125 | 90 | 0.18 |  | 10th-May | 5716
18 |  | Apu Ray | Rk Nagar | Shribhumi | 31 | 31 | 96 | 8 | 88 | 0 | 775 | 95 | 141 | 58 | 164 | 103 | 132 | 125 | 161 | 183 | 181 | 207 | 168 | 188 | 220 | 165 | 217 | 74 | 131 | 216 | 196 | 170 | 209 | 204 | 0.26323 |  | 15th-May | 13287 | 9683
19 |  | Apu Ray | Patharkandi | Shribhumi | 54 | 46 | 151 | 0 | 151 | 2 | 1350 | 262 | 273 | 36 | 198 | 32 | 152 | 292 | 312 | 365 | 362 | 62 | 396 | 323 | 299 | 310 | 346 | 10 | 133 | 334 | 316 | 314 | 305 | 313 | 0.23185 |  | 15th-May | 21433 | 12219
20 |  | Utpal Rabha | Chandrapur | Kamrup M | 24 | 20 | 37 | 3 | 34 | 9 | 600 | 143 | 0 | 43 | 18 | 235 | 305 | 269 | 242 | 308 | 179 | 7 | 44 | 28 | 74 | 181 | 227 | 12 | 38 | 304 | 290 | 281 | 220 | 183 | 0.305 |  | 10th-May | 20799 | 11600
21 |  | Humayun Kabir | Agomani | Dhubri | 7 | 7 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 55 | 41 | 42 | 44 | 46 | 36 | 33 | 13 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Village Completed
22 | NC | Humayun Kabir | Baghbor | Barpeta | 3 | 2 | 3 | 0 | 3 | 3 | 75 | 112 | 132 | 10 | 25 | 82 | 58 | 46 | 83 | 53 | 55 | 31 | 95 | 71 | 45 | 55 | 91 | 57 | 89 | 100 | 74 | 97 | 73 | 89 | 1.1867
23 |  | Tanmoy Dutta | Kampur | Nagaon | 5 | 5 | 6 | 1 | 5 |  | 125 | 93 | 91 | 84 | 118 | 126 | 98 | 133 | 125 | 136 | 128 | 0 | 73 | 123 | 111 | 116 | 124 | 104 | 64 | 60 | 46 | 60 | 33 | 31 | 0.248
|  |  | Total | [7 empty] | 8625 | 1592 | 1719 | 875 | 1923 | 3042 | 3059 | 3032 | 3414 | 2047 | 2875 | 894 | 3091 | 2384 | 2861 | 2764 | 2244 | 1776 | 2083 | 2984 | 2781 | 3031 | 2850 | 2624 | 0.30423

## Onfield_Reservey_Dag
Co-ordinator | Circle Name | District Name | Total Villages | Village Completed | Pending Villages | Data Verification | On-Field | Daily KPI | 1st-Aug | 2nd-Aug | 4th-Aug | 5th-Aug | 6th-Aug | 7th-Aug | 8th-Aug | 9th-Aug | 11th-Aug | 12th-Aug | 13th-Aug | 14th-Aug | 16th-Aug | 18th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | 27th-Aug | 28th-Aug | % of 28th-Aug
Pradip Saikia | Dhemaji | Dhemaji | 8 | 8 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pradip Saikia | Gogamukh | Dhemaji | 18 | 10 | 8 |  | 0 | 0 | 164 | 194 | 159 | 241 | 237 | 149 | 77 | 313 | 55 | 338 | 93 | 190 | 253 | 183 | 31 | 16 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pradip Saikia | Jonai | Dhemaji | 22 | 9 | 13 |  | 0 | 0 | 87 | 0 | 51 | 0 | 153 | 0 | 98 | 118 | 0 | 87 | 0 | 116 | 8 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pradip Saikia | Sissiborgaon | Dhemaji | 10 | 10 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ram Kumar Doley | Dibrugarh West | Dibrugarh | 169 | 17 | 152 | 5 | 41 | 1025 | 0 | 181 | 104 | 320 | 593 | 492 | 463 | 463 | 0 | 328 | 0 | 515 | 397 | 531 | 542 | 214 | 517 | 564 | 583 | 464 | 625 | 561 | 497 | 0.48488
Rupam Jyoti Gogoi | Dibrugarh East | Dibrugarh | 116 | 0 | 116 | 9 | 31 | 775 | 40 | 48 | 34 | 184 | 333 | 279 | 339 | 346 | 0 | 218 | 4 | 318 | 46 | 314 | 325 | 147 | 272 | 290 | 268 | 263 | 300 | 422 | 410 | 0.52903
Rupam Jyoti Gogoi | Moran | Dibrugarh | 60 | 2 | 57 |  | 16 | 400 | 66 | 130 | 135 | 173 | 194 | 267 | 223 | 223 | 174 | 114 | 172 | 166 | 0 | 82 | 141 | 161 | 241 | 207 | 210 | 206 | 219 | 208 | 224 | 0.56
Rupam Jyoti Gogoi | Chabua | Dibrugarh | 104 | 2 | 102 | 7 | 16 | 400 | 0 | 20 | 26 | 12 | 260 | 335 | 199 | 199 | 0 | 75 | 7 | 153 | 153 | 157 | 146 | 60 | 94 | 107 | 206 | 217 | 206 | 128 | 92 | 0.23
Rupam Jyoti Gogoi | Tinsukia | Tinsukia | 13 | 0 | 13 | 7 | 7 | 175 | 0 | 0 | 0 | 33 | 83 | 7 | 120 | 92 | 37 | 36 | 0 | 85 | 150 | 104 | 115 | 27 | 97 | 56 | 35 | 34 | 38 | 40 | 53 | 0.30286
Biprojit Roy | Algapur | Hailakandi | 11 | 1 | 10 | 1 | 6 | 150 | 54 | 28 | 2 | 25 | 66 | 61 | 60 | 68 | 59 | 69 | 7 | 82 | 76 | 62 | 63 | 75 | 34 | 58 | 98 | 83 | 81 | 71 | 52 | 0.34667
Biprojit Roy | Hailakandi | Hailakandi | 7 | 1 | 6 | 1 | 5 | 125 | 53 | 55 | 0 | 37 | 33 | 43 | 47 | 55 | 76 | 65 | 15 | 59 | 60 | 29 | 58 | 63 | 13 | 26 | 66 | 64 | 75 | 62 | 81 | 0.648
Biprojit Roy | Lala | Hailakandi | 2 | 0 | 2 |  | 1 | 25 | 21 | 17 | 0 | 4 | 0 | 8 | 2 | 3 | 5 | 4 | 0 | 4 | 5 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 4 | 3 | 0.12
Biprojit Roy | Katlichera | Hailakandi | 7 | 0 | 7 | 1 | 7 | 175 | 60 | 72 | 0 | 75 | 78 | 96 | 104 | 91 | 105 | 78 | 70 | 97 | 105 | 114 | 92 | 69 | 26 | 59 | 81 | 75 | 88 | 86 | 83 | 0.47429
Biprojit Roy | Badarpur | Shribhumi | 61 | 0 | 61 | 2 | 20 | 500 | 170 | 159 | 36 | 179 | 290 | 319 | 273 | 287 | 290 | 337 | 83 | 315 | 197 | 212 | 210 | 237 | 145 | 199 | 244 | 292 | 272 | 241 | 201 | 0.402
Biprojit Roy | Shribhumi Sadar | Shribhumi | 45 | 1 | 44 | 1 | 5 | 125 | 14 | 30 | 9 | 10 | 62 | 46 | 63 | 79 | 58 | 34 | 35 | 70 | 44 | 45 | 59 | 46 | 24 | 19 | 23 | 58 | 73 | 62 | 18 | 0.144
Biprojit Roy | Nilambazar | Shribhumi | 65 | 0 | 65 | 3 | 11 | 275 | 158 | 148 | 88 | 52 | 41 | 170 | 55 | 108 | 107 | 154 | 88 | 145 | 157 | 110 | 147 | 124 | 22 | 43 | 148 | 95 | 124 | 125 | 90 | 0.32727
Apu Ray | Rk Nagar | Shribhumi | 96 | 8 | 88 | 0 | 17 | 425 | 95 | 141 | 58 | 164 | 103 | 132 | 125 | 161 | 183 | 181 | 207 | 168 | 188 | 220 | 165 | 217 | 74 | 131 | 216 | 196 | 170 | 209 | 204 | 0.48
Apu Ray | Patharkandi | Shribhumi | 151 | 0 | 151 | 2 | 39 | 975 | 262 | 273 | 36 | 198 | 32 | 152 | 292 | 312 | 365 | 362 | 62 | 396 | 323 | 299 | 310 | 346 | 10 | 133 | 334 | 316 | 314 | 305 | 313 | 0.32103
Utpal Rabha | Chandrapur | Kamrup M | 37 | 3 | 34 | 9 | 15 | 375 | 143 | 0 | 43 | 18 | 235 | 305 | 269 | 242 | 308 | 179 | 7 | 44 | 28 | 74 | 181 | 227 | 12 | 38 | 304 | 290 | 281 | 220 | 183 | 0.488
Humayun Kabir | Agomani | Dhubri | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 55 | 41 | 42 | 44 | 46 | 36 | 33 | 13 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Humayun Kabir | Baghbor | Barpeta | 3 | 0 | 3 | 3 | 3 | 75 | 112 | 132 | 10 | 25 | 82 | 58 | 46 | 83 | 53 | 55 | 31 | 95 | 71 | 45 | 55 | 91 | 57 | 89 | 100 | 74 | 97 | 73 | 89 | 1.1867
Tanmoy Dutta | Kampur | Nagaon | 6 | 1 | 5 |  | 2 | 50 | 93 | 91 | 84 | 118 | 126 | 98 | 133 | 125 | 136 | 128 | 0 | 73 | 123 | 111 | 116 | 124 | 104 | 64 | 60 | 46 | 60 | 33 | 31 | 0.62
| Total | [6 empty] | 6050 | 1592 | 1719 | 875 | 1923 | 3042 | 3059 | 3032 | 3414 | 2047 | 2875 | 894 | 3091 | 2384 | 2861 | 2764 | 2244 | 1776 | 2083 | 2984 | 2781 | 3031 | 2850 | 2624 | 0.43372

## FC_Performance Matrix-July-25
1st - 28th Aug Coordinator Progress Report
Co-ordinator Name | Survey Areas | District Name | Surveyor Deployed | Active Surveyor | Dag per Surveyor | Target Dag | 2025-08-01 | 2025-08-02 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-11 | 2025-08-12 | 13th-Aug | 14th-Aug | 19th-Aug | 20th-Aug | 21st-Aug | 22nd-Aug | 23rd-Aug | 25th-Aug | 26th-Aug | % of 26th-Aug Achieved Dags | 27th-Aug | 28th-Aug | % of 28th-Aug Achieved Dags
Dibakar Kalita | Reservey/Naksha | Golaghat | 29 | 20 | 20&25 | 160 | 66 | 163 | 142 | 236 | 238 | 332 | 254 | 223 | 269 | 232 | 172 | 254 | 194 | 224 | 241 | 207 | 210 | 0 | 78 | 0.4875 | 113 | 85 | 0.53125
Tanmoy Dutta | Naksha/NC | Nagaon/Hojai | 36 | 35 | 20&25 | 770 | 93 | 140 | 91 | 244 | 537 | 613 | 616 | 287 | 532 | 508 | 0 | 531 | 316 | 266 | 130 | 73 | 150 | 158 | 370 | 0.48052 | 324 | 331 | 0.42987
Humayun Kabir | Reservey/Naksha/NC | Bongaigaon/Nalbari/Barpeta/Dhubri | 69 | 61 | 20&25 | 1415 | 167 | 321 | 16 | 152 | 432 | 554 | 520 | 350 | 450 | 161 | 44 | 378 | 308 | 405 | 205 | 198 | 250 | 196 | 480 | 0.33922 | 471 | 543 | 0.38375
Ram Kumar Doley | Reservey | Dibrugarh | 55 | 46 | 25 | 1375 | 0 | 181 | 104 | 320 | 593 | 492 | 463 | 463 | 0 | 328 | 0 | 515 | 542 | 214 | 517 | 564 | 583 | 464 | 625 | 0.45455 | 561 | 497 | 0.36145
Rupam Jyoti Gogoi | Reservey/Naksha | Dibrugarh/Tinsukia/Sivsagar | 76 | 76 | 25 | 2400 | 40 | 68 | 34 | 229 | 676 | 621 | 658 | 637 | 37 | 218 | 11 | 556 | 586 | 234 | 463 | 453 | 509 | 720 | 763 | 0.31792 | 758 | 779 | 0.32458
Biprojit Roy | Reservey | Shribhumi/Hailakandi | 78 | 68 | 25 | 1925 | 530 | 509 | 135 | 382 | 570 | 743 | 604 | 691 | 700 | 741 | 298 | 772 | 637 | 617 | 242 | 404 | 668 | 675 | 721 | 0.37455 | 651 | 528 | 0.27429
Utpal Rabha | Reservey | Kamrup M | 24 | 22 | 25 | 720 | 143 | 0 | 43 | 18 | 235 | 305 | 269 | 242 | 308 | 179 | 7 | 44 | 181 | 227 | 12 | 38 | 304 | 290 | 281 | 0.39028 | 220 | 183 | 0.25417
Apu Ray | Reservey | Shribhumi | 85 | 81 | 25 | 2125 | 357 | 414 | 94 | 362 | 135 | 284 | 417 | 473 | 548 | 543 | 269 | 564 | 475 | 563 | 84 | 264 | 550 | 512 | 484 | 0.22776 | 514 | 517 | 0.24329
Pradip Saikia | NC Forest Reservey | Dhemaji | 29 | 26 | 25 | 0 | 251 | 194 | 210 | 241 | 390 | 149 | 175 | 431 | 55 | 425 | 93 | 306 | 31 | 16 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project-Overview
Present Status |  | Work in Progress
Item | Details | Activity | Status
Survey Completed (NC Villages) | 531 villages | Re-Survey Operations | Ongoing in 926 villages across 6 districts
Survey Completed (NC Forest Villages) | 64 villages
Total Property Details (NAKSHA) | 251067 | NC Survey Operations | Ongoing in 6 villages
Properties Surveyed (NAKSHA Project) | 87484 | NAKSHA Survey Operations | Active in 37 wards
Pending Property Details | 163583
ULBs Covered Under NAKSHA | 10 ULBs (Total Wards: 155)
Wards Completed Under NAKSHA | 116 Wards
Property Completion-Naksha |  | Reservey Villages Details | Count
Properties Completed - Nagaon | 16616 (51074) | Total Villages (Resurvey) | 926
Properties Completed - Hojai | 5601 (16741) | Villages Completed(Reservey) | 36
Properties Completed - Barpeta Road | 8952 (19767) | Villages in Data Verification Process | 58
Properties Completed - Bongaigaon | 12706 (41125) | Ongoing Villages | 287
Properties Completed - Abhayapuri | 5816 (7987)
Properties Completed - Nalbari | 8918 (35835)
Properties Completed - Mangaldoi | 4559 (21648) | Field Coordinator | Active Villages | Below 50% Completion | Above 50% Completion | Above 80% Completion | Almost Completed
Properties Completed - Dhekiajuli | 8976 (16725) | Apu Ray | 59 | 29 | 18 | 5 | 7
Properties Completed - Sivasagar | 10343 (19485) | Biprojit Roy | 72 | 0 | 53 | 12 | 7
Properties Completed - Golaghat | 4903 (20678) | Rupam Gogoi | 69 | 29 | 33 | 7 | 0
Re-Survey Villages Completed |  | Raam Doley | 51 | 21 | 22 | 0 | 8
Re-Survey Villages Completed | 37 villages | Utpal Rabha | 14 | 11 | 3 | 0 | 5
Re-Survey Circles Covered | Dibrugarh West, Chandrapur, Chabua,Kampur,Moran,algapur,sadar,algapur,Hailakandi | Pradip Saikia | 0 | 0 | 0 | 0 | 0
HRs Details |  | Dibakar Kalita | 19 | 8 | 11
Active Teams | 551
HRs in Survey/Re-Survey | 384
HRs in NC Survey | 6
HRs in NAKSHA | 161
Additional HRs Ready to Deploy | 49
Assistant Surveyors at Worksites | 551
Re-Survey Work Issues |  | NAKSHA Project Issues
Problem Area | Description | Problem Area | Description
Network Connectivity | Non-availability in remote areas | Municipality Coordination | Lack of presence of Municipality Member/Text Collector delays verification
HR Challenges | Public reluctance, lack of cooperation | Multiple Site Visits | Owners unaware of survey schedule, leading to repeated site visits
Device Problems | CORS ID auth issues, Trimble malfunctions | Surveyor Access Restrictions | Owners allow survey only when accompanied by a Municipality Member
Vehicle Issues | Breakdowns and transport unavailability | Data Synchronization | Network issues causing delays
Weather Challenges | Heavy rain, extreme heat hampering field work | Property Owner Availability | Unavailable during visits, slowing verification
|  | Public Awareness | Lack of understanding causing resistance/misinformation
|  | Weather & Logistics | Rains, heat, transport issues

## Less than 16 Dags
SURVEYOR COLLECTED LESS THEN 16 DAG ON 27th-Aug
Sl No | Field Coordinator | Name of the Hired Surveyor | Batch No | Circle Name | District Name | Dag
1 | RAM DOLEY | Pradeep Sarkar | Batch 1 | Dibrugarh West | Dibrugarh | 14
2 | RAM DOLEY | Nilutpal Dutta | Batch 1 | Dibrugarh West | Dibrugarh | 10 | Today present 468
3 | RAM DOLEY | Mymon Dihingia | Batch 1 | Dibrugarh West | Dibrugarh | 6 | 0 dag - 175
4 | RAM DOLEY | Nilutpal Gogoi | Batch 1 | Dibrugarh West | Dibrugarh | 10 | 1 to 5 - 46
5 | RAM DOLEY | Udipta Changmai | Batch 1 | Dibrugarh West | Dibrugarh | 14 | 6 to 15 - 176
6 | RAM DOLEY | Mukti Phukan | Batch 1 | Dibrugarh West | Dibrugarh | 15 | 16 or greater - 71
7 | RAM DOLEY | Manakh Jyoti Borgohain | Batch 1 | Dibrugarh West | Dibrugarh | 7
8 | BIPROJIT ROY | Robiul Hussain | Batch 2 | Badarpur | Karimganj | 4 | Total rover used - 237
9 | APU RAY | Shoib Akter Mazumder | Batch 3 | RK nagar | Karimganj | 10 | Total points collected - 13910
10 | BIPROJIT ROY | Koyes Ahmed Barbuiya | Batch 3 | Algapur | Hailakandi | 7 | Total surveyor present - 335
11 | APU RAY | Novendu Seal | Batch 3 | RK nagar | Karimganj | 5 | Surveyors collected more than 50 points - 129
12 | BIPROJIT ROY | Pradip Riang | Batch 3 | Algapur | Hailakandi | 3 | % of Surveyors collect more than 50 points today - 38.50
13 | BIPROJIT ROY | Basith Ahmed Mazarbhuiya | Batch 3 | Algapur | Hailakandi | 9
14 | UTPAL RABHA | Suju Kr Gayari | Batch 3 | Chandrapur | Kamrup M | 9
15 | RAM DOLEY | Xavier Hajowar | Batch 4 | Dibrugarh West | Dibrugarh | 8
16 | RAM DOLEY | Jahangir Hussain | Batch 4 | Dibrugarh West | Dibrugarh | 6
17 | BIPROJIT ROY | Bayshali Das | Batch 4 | Nilambazar | Karimganj | 5
18 | BIPROJIT ROY | Supriyo Das | Batch 4 | Hailakandi | Hailakandi | 6
19 | BIPROJIT ROY | Anupom Sarma | Batch 4 | Algapur | Hailakandi | 12
20 | BIPROJIT ROY | Suman Malakar | Batch 4 | Lala | Hailakandi | 3
21 | APU RAY | Arup Goswami | Batch 4 | Patharkandi | Karimganj | 7
22 | BIPROJIT ROY | Annu Arddao | Batch 4 | Shribhumi Sadar | Karimganj | 3
23 | APU RAY | Jyotisman Deka | Batch 4 | Patharkandi | Karimganj | 12
24 | RAM DOLEY | Bipul Das | Batch 5 | Dibrugarh West | Dibrugarh | 11
25 | RAM DOLEY | Argeng Basumatary | Batch 5 | Dibrugarh West | Dibrugarh | 5
26 | RAM DOLEY | Khandakar Badarat Jaman | Batch 5 | Dibrugarh West | Dibrugarh | 7
27 | RAM DOLEY | Niranjan Kumar Ray | Batch 5 | Dibrugarh West | Dibrugarh | 15
28 | RAM DOLEY | Subilal Narzary | Batch 5 | Dibrugarh West | Dibrugarh | 10
29 | RAM DOLEY | Swmkwar Daimary | Batch 5 | Dibrugarh West | Dibrugarh | 10
30 | APU RAY | Rezanuj Zaman | Batch 5 | Patharkandi | Karimganj | 10
31 | RAM DOLEY | Archana Roy | Batch 5 | Dibrugarh West | Dibrugarh | 6
32 | RAM DOLEY | Bonashmita Senapoti | Batch 5 | Dibrugarh West | Dibrugarh | 10
33 | BIPROJIT ROY | Josmaidao Thaosen | Batch 5 | Shribhumi Sadar | Karimganj | 4
34 | UTPAL RABHA | Rumi Baruah | Batch 5 | Chandrapur | Kamrup M | 5
35 | BIPROJIT ROY | Lasmi Debragede | Batch 5 | Shribhumi Sadar | Karimganj | 4
36 | BIPROJIT ROY | Rahul Langthasa | Batch 5 | Shribhumi Sadar | Karimganj | 6
37 | BIPROJIT ROY | Sunabi Johori | Batch 5 | Shribhumi Sadar | Karimganj | 1
38 | RAM DOLEY | Sanjib Saikia | Batch 5 | Dibrugarh West | Dibrugarh | 15
39 | APU RAY | Kamal Rajbongshi | Batch 5 | Patharkandi | Karimganj | 5
40 | APU RAY | Sanjoy Shyam | Batch 5 | Patharkandi | Karimganj | 10
41 | RUPAM JYOTI GOGOI | Madhuri Khakhlari | Batch 5 | Dibrugarh East | Dibrugarh | 14
42 | UTPAL RABHA | Abdul Mazid Mondal | Batch 6 | Chandrapur | Kamrup M | 15
43 | UTPAL RABHA | Abdul Sarwer Mintu | Batch 6 | Chandrapur | Kamrup M | 10
44 | APU RAY | Deep Jyoti Sarania | Batch 6 | Patharkandi | Karimganj | 8
45 | UTPAL RABHA | Mohibul Islam | Batch 6 | Chandrapur | Kamrup M | 11
46 | UTPAL RABHA | Prasenjit Barman | Batch 6 | Chandrapur | Kamrup M | 13
47 | BIPROJIT ROY | Samsul Hoque | Batch 6 | Badarpur | Karimganj | 4
48 | UTPAL RABHA | Jillur Rahman | Batch 6 | Chandrapur | Kamrup M | 8
49 | BIPROJIT ROY | Nur Alom Sheikh | Batch 6 | Badarpur | Karimganj | 1
50 | RAM DOLEY | Subhash Chandra Das | Batch 6 | Dibrugarh West | Dibrugarh | 15
51 | BIPROJIT ROY | Altaf Hussain Barbhuiyan | Batch 6 | Katlichera | Hailakandi | 6
52 | APU RAY | Azmal Hussain Choudhury | Batch 6 | RK nagar | Karimganj | 5
53 | APU RAY | Dhrubojyoti Roy | Batch 6 | RK nagar | Karimganj | 10
54 | APU RAY | Sujata Das | Batch 6 | RK nagar | Karimganj | 14
55 | BIPROJIT ROY | Soma Nath | Batch 6 | Hailakandi | Hailakandi | 15
56 | BIPROJIT ROY | Abdul Maleque | Batch 6 | Badarpur | Karimganj | 8
57 | BIPROJIT ROY | Ashan Ali | Batch 6 | Badarpur | Karimganj | 13
58 | BIPROJIT ROY | Hasen Ali | Batch 6 | Badarpur | Karimganj | 12
59 | UTPAL RABHA | Aminul Hoque | Batch 6 | Chandrapur | Kamrup M | 15
60 | APU RAY | Nayanjyoti kalita | Batch 6 | Patharkandi | Karimganj | 8
61 | APU RAY | Imran Hussain | Batch 6 | Patharkandi | Karimganj | 2
62 | APU RAY | Hemonto Paw | Batch 6 | Patharkandi | Karimganj | 10
63 | APU RAY | Rajdeep Das | Batch 7 | RK nagar | Karimganj | 10
64 |  | Dipak Airio | Batch 7 | Moran | Dibrugarh | 14
65 | RAM DOLEY | Anuradha Saikia | Batch 7 | Dibrugarh West | Dibrugarh | 10
66 | RUPAM JYOTI GOGOI | Bulbul Borah | Batch 7 | Dibrugarh East | Dibrugarh | 5
67 | RUPAM JYOTI GOGOI | Karan Boruah | Batch 7 | Dibrugarh East | Dibrugarh | 11
68 | RUPAM JYOTI GOGOI | Manidhar Pegu | Batch 7 | Dibrugarh East | Dibrugarh | 13
69 | RAM DOLEY | Dharamjit Pegu | Batch 7 | Dibrugarh West | Dibrugarh | 14
70 | RAM DOLEY | Bhargav Bormudoi | Batch 7 | Dibrugarh West | Dibrugarh | 10
71 | APU RAY | Chiraj Morang | Batch 7 | Patharkandi | Karimganj | 4
72 | APU RAY | Sukanta Das | Batch 8 | RK nagar | Karimganj | 12
73 | RUPAM JYOTI GOGOI | Luminous Brahma | Batch 8 | Dibrugarh East | Dibrugarh | 7
74 | BIPROJIT ROY | Mridul Boruah | Batch 8 | Badarpur | Karimganj | 8
75 | RAM DOLEY | Mriganka Das | Batch 8 | Dibrugarh West | Dibrugarh | 10
76 | RAM DOLEY | Anirban Saikia | Batch 8 | Dibrugarh West | Dibrugarh | 9
77 | RAM DOLEY | Anjan Jyoti Bora | Batch 8 | Dibrugarh West | Dibrugarh | 15
78 | BIPROJIT ROY | Nabajyoti Kalita | Batch 8 | Badarpur | Karimganj | 7
79 | BIPROJIT ROY | Abul Hussain | Batch 8 | Badarpur | Karimganj | 15
80 | UTPAL RABHA | Swapnali Baruah | Batch 8 | Chandrapur | Kamrup M | 9
81 | RUPAM JYOTI GOGOI | Madhab Saikia | Batch 8 | Dibrugarh East | Dibrugarh | 11
82 | RUPAM JYOTI GOGOI | Biki Kumar Pegu | Batch 8 | Dibrugarh East | Dibrugarh | 14
83 | APU RAY | Gunindra Deuri | Batch 8 | Patharkandi | Karimganj | 6
84 | RUPAM JYOTI GOGOI | Kapil Dev Brahma | Batch 8 | Dibrugarh East | Dibrugarh | 5
85 | RUPAM JYOTI GOGOI | Bhabesh Taid | Batch 9 | Dibrugarh East | Dibrugarh | 6
86 | RUPAM JYOTI GOGOI | Durgeswar Pegu | Batch 9 | Dibrugarh East | Dibrugarh | 14
87 | APU RAY | Amar Jyoti Baruah | Batch 9 | Patharkandi | Karimganj | 5
88 | UTPAL RABHA | Bulu Prabha Saloi | Batch 9 | Chandrapur | Kamrup M | 12
89 | BIPROJIT ROY | Ataur Rahman | Batch 9 | Badarpur | Karimganj | 10
90 | BIPROJIT ROY | Hemanta Boro | Batch 9 | Badarpur | Karimganj | 15
91 | APU RAY | Tarik Ahmed | Batch 9 | Patharkandi | Karimganj | 5
92 | RUPAM JYOTI GOGOI | Bipul Sonowal | Batch 9 | Dibrugarh East | Dibrugarh | 12
93 | RUPAM JYOTI GOGOI | Kukil Deuri | Batch 9 | Dibrugarh East | Dibrugarh | 15
94 | RUPAM JYOTI GOGOI | Bornalee Borah | Batch 9 | Dibrugarh East | Dibrugarh | 10
95 | RUPAM JYOTI GOGOI | Rupi Konwar | Batch 9 | Dibrugarh East | Dibrugarh | 12
96 | RUPAM JYOTI GOGOI | Dimpal Dutta | Batch 9 | Dibrugarh East | Dibrugarh | 13
97 | RUPAM JYOTI GOGOI | Joyprakash Gogoi | Batch 9 | Dibrugarh East | Dibrugarh | 15
98 | RUPAM JYOTI GOGOI | Khairul Hussain | Batch 9 | Dibrugarh East | Dibrugarh | 14
99 | RAM DOLEY | Pintu Tanti | Batch 9 | Dibrugarh West | Dibrugarh | 12
100 | RAM DOLEY | Pulin Bhorai | Batch 9 | Dibrugarh West | Dibrugarh | 8
101 | RAM DOLEY | Joy Pegu | Batch 9 | Dibrugarh West | Dibrugarh | 12
102 | RUPAM JYOTI GOGOI | Archana Sonowal | Batch 9 | Dibrugarh East | Dibrugarh | 4
103 | RUPAM JYOTI GOGOI | Bishwawanti Sonowal | Batch 9 | Tinsukia | Tinsukia | 15
104 | BIPROJIT ROY | Bitu Buragohain | Batch 10 | Badarpur | Karimganj | 7
105 | RUPAM JYOTI GOGOI | Jimbani Dutta | Batch 10/Batch 11 | Dibrugarh East | Dibrugarh | 6
106 | APU RAY | Karishma Ahmed | Batch 10/Batch 11 | Patharkandi | Karimganj | 11
107 | RAM DOLEY | Rajdeep Payang | Batch 10 | Dibrugarh West | Dibrugarh | 10
108 | BIPROJIT ROY | Debajyoti Gogoi | Batch 10 | Badarpur | Karimganj | 6
109 | RAM DOLEY | Rashmi Konwar | Batch 10 | Dibrugarh West | Dibrugarh | 11
110 | RUPAM JYOTI GOGOI | Bhaskar Saikia | Batch 10 | chabua | Dibrugarh | 4
111 | RUPAM JYOTI GOGOI | Gitika Phukan | Batch 10 | chabua | Dibrugarh | 3
112 | RAM DOLEY | Shibani Saikia | Batch 10/Batch 11 | Dibrugarh West | Dibrugarh | 7
113 | RAM DOLEY | Rantu Konwar | Batch 10 | Dibrugarh West | Dibrugarh | 15
114 | RAM DOLEY | Amrit Narah | Batch 10 | Dibrugarh West | Dibrugarh | 11
115 | RUPAM JYOTI GOGOI | Minakshi Neog | Batch 10 | chabua | Dibrugarh | 5
116 | UTPAL RABHA | Md Abdus Salam | Batch 10 | Chandrapur | Kamrup M | 1
117 | APU RAY | Sulaiman Ali | Batch 10 | Patharkandi | Karimganj | 8
118 | RUPAM JYOTI GOGOI | Poonam Barman | Batch 11 | Tinsukia | Tinsukia | 14
119 | RUPAM JYOTI GOGOI | Joyprasad Taid | Batch 11 | Chabua | Dibrugarh | 3
120 | BIPROJIT ROY | Bidyut Dihingia | Batch 11 | Badarpur | Karimganj | 8
121 | APU RAY | Nurjahan Begum | Batch 12 | Patharkandi | Karimganj | 10
122 | APU RAY | Sopikul Hoque | Batch 12 | Patharkandi | Karimganj | 8
123 | BIPROJIT ROY | Abdul Wahab | Batch 12 | Badarpur | Karimganj | 7
124 | APU RAY | Tafazul Haque | Batch 12 | Patharkandi | Karimganj | 5
125 | APU RAY | Bhrigu Das | Batch 12 | Patharkandi | Karimganj | 13
126 | RUPAM JYOTI GOGOI | Mokibul Islam | Batch 12 | chabua | Dibrugarh | 6
127 | RUPAM JYOTI GOGOI | Shahidul Islam | Batch 12 | chabua | Dibrugarh | 9
128 | RUPAM JYOTI GOGOI | Abidul Islam | Batch 12 | chabua | Dibrugarh | 15
129 | BIPROJIT ROY | Aminul Haque Laskar | Batch 12 | Katlichera | Hailakandi | 10
130 | RUPAM JYOTI GOGOI | Arafat Hossain | BATCH 13 | chabua | Dibrugarh | 13
131 | RUPAM JYOTI GOGOI | Bishal Das | BATCH 13 | Chabua | Dibrugarh | 4
132 | RUPAM JYOTI GOGOI | Bismita Deka | BATCH 13 | chabua | Dibrugarh | 5
133 | RUPAM JYOTI GOGOI | Hiranya Kumar Gogoi | BATCH 13 | chabua | Dibrugarh | 6
134 |  | Jalaluddin Ahmed | BATCH 13 | moran | Dibrugarh | 8
135 | RUPAM JYOTI GOGOI | Joydeep Saikia | BATCH 13 | chabua | Dibrugarh | 3
136 |  | Khaza Faruque Talukdar | BATCH 13 | moran | Dibrugarh | 15
137 |  | Majad Ali | BATCH 13 | moran | Dibrugarh | 5
138 | BIPROJIT ROY | Mirjan Ahmed Laskar | BATCH 13 | Algapur | Hailakandi | 11
139 |  | Priyanka Hazarika | BATCH 13 | moran | Dibrugarh | 14
140 |  | Rahim Badsha | BATCH 13 | moran | Dibrugarh | 11
141 |  | Rupali Nath | BATCH 13 | Moran | Dibrugarh | 4
142 |  | Saddam Hussain | BATCH 13 | moran | Dibrugarh | 10
143 |  | Samidul Islam | BATCH 13 | moran | Dibrugarh | 14
144 |  | Sher Golam Rabbani | BATCH 13 | moran | Dibrugarh | 13
145 | RUPAM JYOTI GOGOI | Shimangshu Baruah | BATCH 13 | Tinsukia | Tinsukia | 2
146 |  | Sirajul Hoque | BATCH 13 | Moran | Dibrugarh | 13
147 | APU RAY | Sumon Kundu | BATCH 13 | RK nagar | Karimganj | 11
148 | APU RAY | Laku Das | BATCH 6 | Patharkandi | Karimganj | 1
149 | RUPAM JYOTI GOGOI | Jitul doley | Batch 7 | tinsukia | TINSUKIA | 11
150 | RUPAM JYOTI GOGOI | Manjil Payeng | Batch 9 | tinsukia | TINSUKIA | 1
151 | RUPAM JYOTI GOGOI | Anamika buragohain | Batch 5 | tinsukia | TINSUKIA | 5
152 | RUPAM JYOTI GOGOI | NISHIGANDHA GOGOI | Batch 12 | tinsukia | TINSUKIA | 5
153 | APU RAY | Bikash Singha | Batch 14 | Patharkandi | Karimganj | 9
154 | APU RAY | Furkan Ahmed | Batch 14 | Patharkandi | Karimganj | 4
155 | APU RAY | H. Debit Singha | Batch 14 | Patharkandi | Karimganj | 6
156 | APU RAY | Ijaj Ahmed Laskar | Batch 14 | Patharkandi | Karimganj | 8
157 | APU RAY | Mabrur Ahmed Barbhuiya | Batch 14 | Patharkandi | Karimganj | 10
158 | APU RAY | Probhakar Das | Batch 14 | Patharkandi | Karimganj | 4
159 | APU RAY | Sh Roshan Singha | Batch 14 | Patharkandi | Karimganj | 10
160 | APU RAY | T Nganthoiba Singfha | Batch 14 | Patharkandi | Karimganj | 7
161 | APU RAY | Tinki Nag | Batch 14 | Patharkandi | Karimganj | 5
162 | APU RAY | Sirajul Abedin Choudhury | Batch 15 | Patharkandi | Karimganj | 7
163 | APU RAY | Debangli Das | Batch 14 | Patharkandi | Karimganj | 6
164 | APU RAY | Dabit Singha | Batch 14 | Patharkandi | Karimganj | 8
165 | BIPROJIT ROY | A S Imdadur Rahman | Batch 15 | Nilambazar | Karimganj | 15
166 | APU RAY | Susmita Rani Das | Batch 15 | Patharkandi | Karimganj | 6
167 | APU RAY | L. Bikram Singha | Batch 14 | Patharkandi | Karimganj | 15
168 | BIPROJIT ROY | Shakir Chodhury | Batch 15 | Nilambazar | Karimganj | 5
169 | APU RAY | Suresh Kumar Singha | Batch 14 | Patharkandi | Karimganj | 6
170 | BIPROJIT ROY | Gulzar Hussain | Batch 15 | Nilambazar | Karimganj | 5
171 | BIPROJIT ROY | Nandita Chanda | Batch 15 | Nilambazar | Karimganj | 4
172 | BIPROJIT ROY | Juber Ahmed | Batch 14 | Nilambazar | Karimganj | 6
173 | BIPROJIT ROY | Drishti Dey | Batch 15 | Nilambazar | Karimganj | 5
174 | BIPROJIT ROY | Mahfuz Hussan | Batch 15 | Nilambazar | Karimganj | 6
175 | APU RAY | Raja Iqbal | Batch 15 | RK nagar | Karimganj | 13
176 | APU RAY | Abdul Ahad | Batch 15 | RK nagar | Karimganj | 8
177 | APU RAY | Sourab Dey | Batch 15 | RK nagar | Karimganj | 8
178 | APU RAY | Satyabrata Deb | Batch 15 | RK nagar | Karimganj | 10
179 | APU RAY | Jali Das | Batch 14 | RK nagar | Karimganj | 14
180 | BIPROJIT ROY | Prabal Chakraborty | Batch 15 | Nilambazar | Karimganj | 6
181 | BIPROJIT ROY | Sanatambi Singha | Batch 14 | Badarpur | Karimganj | 10
182 | BIPROJIT ROY | Subir Malakar | Batch 14 | Badarpur | Karimganj | 10
183 | BIPROJIT ROY | Armita Paul | Batch 14 | Badarpur | Karimganj | 12
184 | BIPROJIT ROY | Gitanjali Singha | Batch 14 | Badarpur | Karimganj | 11
185 | BIPROJIT ROY | Debosree Dhar | Batch 14 | Katlichera | Hailakandi | 10
186 | BIPROJIT ROY | H. Abhijit Singha | Batch 14 | Hailakandi | Hailakandi | 15
187 | BIPROJIT ROY | H. Roshan Singha | Batch 14 | Hailakandi | Hailakandi | 15
188 | BIPROJIT ROY | Abdul Mukit Laskar | Batch 15 | Katlichera | Hailakandi | 13
189 | BIPROJIT ROY | Abu Saleh Ubaidulla Barbhuiya | Batch 15 | Katlichera | Hailakandi | 10
190 | BIPROJIT ROY | Aksor Ahmed Choudhury | Batch 15 | Algapur | Hailakandi | 10
191 | HUMAYUN KABIR | Jonmejoy Hajowary | Batch 3 | BONGAIGAON | BONGAIGAON | 7
192 | HUMAYUN KABIR | Sontosh Ali | Batch 3 | BONGAIGAON | BONGAIGAON | 15
193 | HUMAYUN KABIR | Momer Ali | Batch 3 | BONGAIGAON | BONGAIGAON | 8
194 | HUMAYUN KABIR | Arif Hussain | Batch 3 | BARNAGAR | BARPETA | 14
195 | HUMAYUN KABIR | Saiful Islam | Batch 3 | BARNAGAR | BARPETA | 12
196 |  | Hridoy Horsid Bora | Batch 3 | GOLAGHAT | GOLAGHAT | 14
197 |  | Jayanta Hazarika | Batch 3 | GOLAGHAT | GOLAGHAT | 15
198 | SADULLA HUSSAIN | Abhijit Thakuria | Batch 3 | NALBARI | NALBARI | 10
199 | SADULLA HUSSAIN | Jeherul Islam | Batch 3 | NALBARI | NALBARI | 14
200 | SADULLA HUSSAIN | Niran Kathar | Batch 3 | NALBARI | NALBARI | 10
| SADULLA HUSSAIN | Pratul Kalita | Batch 3 | NALBARI | NALBARI | 11
|  | Subhra Jyoti Baruah | Batch 4 | GOLAGHAT | GOLAGHAT | 9
| HUMAYUN KABIR | Dipankar Roy | Batch 4 | BONGAIGAON | BONGAIGAON | 8
| HUMAYUN KABIR | Mostafizur Rahman | Batch 4 | BONGAIGAON | BONGAIGAON | 11
| HUMAYUN KABIR | Sahin Alom | Batch 4 | BONGAIGAON | BONGAIGAON | 15
| SADULLA HUSSAIN | Dhrubajyoti Barman | Batch 4 | NALBARI | NALBARI | 10
| SADULLA HUSSAIN | Hasimuddin Choudhury | Batch 4 | NALBARI | NALBARI | 14
| SADULLA HUSSAIN | Islam Ali | Batch 4 | NALBARI | NALBARI | 10
| SADULLA HUSSAIN | Kishor Haloi | Batch 4 | NALBARI | NALBARI | 12
| HUMAYUN KABIR | Robiul Hoque | Batch 4 | BARNAGAR | BARPETA | 3
| TANMOY DUTTA | Eusuf Ali | Batch 4 | HOJAI | HOJAI | 8
| SADULLA HUSSAIN | Jamir Uddin | Batch 5 | NALBARI | NALBARI | 8
| SADULLA HUSSAIN | Merajul Ahmed | Batch 5 | NALBARI | NALBARI | 8
| SADULLA HUSSAIN | Mostafizur rohman | Batch 5 | NALBARI | NALBARI | 8
| SADULLA HUSSAIN | Haidar Ali | Batch 5 | NALBARI | NALBARI | 9
| SADULLA HUSSAIN | Ijajul Haque | Batch 5 | NALBARI | NALBARI | 8
| SADULLA HUSSAIN | Nurul Islam Choudhury | Batch 5 | NALBARI | NALBARI | 8
|  | Himangkan Pegu | Batch 5 | GOLAGHAT | GOLAGHAT | 12
| HUMAYUN KABIR | Dhritiman RayMedhi | Batch 5 | BARNAGAR | BARPETA | 15
| HUMAYUN KABIR | Basanta Kumar Owary | Batch 5 | BARNAGAR | BARPETA | 15
| KUNAL HAZARIKA | Prantik Deka | Batch 6 | Mangaldoi | DARRANG | 14
| TANMOY DUTTA | Biswajit Borah | Batch 5 | KAMPUR | NAGAON | 15